## 045-A-MSD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Salman Jaffer | As experienced in the existing unit, equivalent lines have some issues with corrosion due to dead leg. Therefore, heat tracing is considered during FEED. Refer to line (045-16"-P1003-B30-Ist) of BRA-226730 sheet 3 of 19. Please consider Note 1.
2 | Callout | 1 | Robert.Kawitzki | equipment numbering as per BMPS-A8 - typ comment
3 | Text Box | 1 | MAK | General Comment: The equipment data shall be placed in alignment with the location of the equipment as possible.
4 | Callout | 1 | Salman Jaffer | General Comment: Use full tag number
5 | Text Box | 1 | MAK | General Comments applies to all MSDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 004 on all the sheets. 3. Always use NTS for MSD scale. 4. Always use A1 for MSD border size.
6 | Callout | 1 | Saeed Taher | Refer to Bid Queries T1380 & T1632
7 | Text Box | 1 | Mahdi Ali | Scale: NTS Size: A1 TTL SHT: 004
8 | Callout | 1 | Salman Jaffer | Show FV0009 per BMPS-A-50003
9 | Callout | 1 | Salman Jaffer | Show the destination
10 | Callout | 1 | Salman Jaffer | SRU Tail Gas line should be heat traced. Please review requirement of Note 1 for this stream.
11 | Callout | 1 | Robert.Kawitzki | text height and width as per BMPS-A8 - typ comment
12 | Text Box | 1 | balagangadhar.k | Update the process flow scheme as per latest PFD. All Equipment numbers to be updated as per latest equipment list.
13 | Text Box | 1 | Mahdi Ali | Use latest PFD border
14 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.