## 045-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | 1
2 | Call-out | 1 | MAK | 2
3 | Call-out | 1 | MAK | 3
4 | Call-out | 1 | MAK | 4
5 | Call-out | 1 | MAK | Are these nos. as per the agreed equipment list?
6 | Text Box | 1 | balagangadhar.k | Comments provided on Unit 044 & 045 PFD are applicable to both Units.
7 | Call-out | 1 | MAK | Delete #
8 | Call-out | 1 | MAK | Equipment numbers shall be entered fully, e.g. 045P0001, 045P0002, 045P0007.
9 | Callout | 1 | Salman Jaffer | FEED have two shells for this exchanger and in this PFD it is changed to one. Confirm with Licenser.
10 | Text Box | 1 | MAK | General Comment: The equipment data shall be placed in alignment with the location of the equipment as possible.
11 | Text Box | 1 | MAK | General Comments applies to all PFDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 010 on all the sheets. 3. Always use NTS for PFD scale. 4. Always use A1 for PFD border size.
12 | Call-out | 1 | MAK | General Comments: - # shall never be used, only 4TGTU & 3TGTU shall be entered. - Unit Nos. shall be entered correctly, e.g. 045, 044.
13 | Text Box | 1 | MAK | Move and align
14 | Text Box | 1 | MAK | Move and align
15 | Text Box | 1 | BD Mori | Please resize & modify the graphics for better presentation.
16 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.