## 049-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Salman Jaffer | #1&2SGPs
2 | Call-out | 1 | MAK | 1
3 | Call-out | 1 | MAK | 2
4 | Call-out | 1 | MAK | 3
5 | Call-out | 1 | MAK | 4
6 | Callout | 1 | Salman Jaffer | 50 psig Steam
7 | Callout | 1 | Syed Ahmed | Add : E
8 | Callout | 1 | Syed Ahmed | check the stream number, as per 3ARU stream data sheet, it must be 19.
9 | Text Box | 1 | balagangadhar.k | Comments provided on Unit 048 & 049 PFD are applicable to both Units.
10 | Call-out | 1 | MAK | Delete
11 | Call-out | 1 | MAK | Delete #
12 | Callout | 1 | Syed Ahmed | Demin water pressure as per stream data sheet is 15 psig and lean Amine pressure is 78 psig. please check
13 | Text Box | 1 | Mahdi Ali | Do not use FEED drawing numbers
14 | Text Box | 1 | MAK | General Comment: The equipment data shall be placed in alignment with the location of the equipment as possible.
15 | Text Box | 1 | MAK | General Comments applies to all PFDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 003 on all the sheets. 3. Always use NTS for PFD scale. 4. Always use A1 for PFD border size.
16 | Callout | 1 | Syed Ahmed | Keep this valve black as per BMPS-A-50003, and mentioned on the line (NNF)
17 | Callout | 1 | Syed Ahmed | Keep this valve black as per BMPS-A-50003, and remove one valve.
18 | Callout | 1 | Syed Ahmed | Keep this valve black as the LP condensate normal routing is to #3TGTU LP condensate flash drum V0013, in addition mentioned on the line NFF( as per BMPS-a-50003).
19 | Callout | 1 | Syed Ahmed | provide number for this equipment
20 | Text Box | 1 | Mahdi Ali | Remove '#' from unit abbreviation.
21 | Callout | 1 | Salman Jaffer | Show PFD number inside the box and keep Note 17 outside the box
22 | Text Box | 1 | BD Mori | This unit PFDs were prepared during FEED, based on the Licensor EDP PFDs. The PFDs were reviewed by Licensor, Bapco and FEED contractor. The process flow configuration was finalized based on the reviews, Bapco’s operating experience with similar units, lessons learned and industry best practices. The PFDs have also under gone Hazop at EDP and FEED stage. Therefore, the deletion of amine tanks, associated facilities and process modifications, to the FEED stage PFDs are not acceptable. TTSJV shall discuss any changes to the FEED PFDs and P&IDs before it is issued in EPC. TTSJV shall also clearly mark such changes and obtain Owner’s approval. If any PFD and P&ID is issued without Owner’s approval, the transmittal shall be summarily rejected.
23 | Text Box | 1 | Mahdi Ali | Unit number shall have 3 digits
24 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.