## 050-G-DAT-55001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Isamu | Please follow and apply the same comments made on 019-G-DAT-00007-001-RAP where releavant
2 | Call-out | 1 | MAK | These pumps belong to Unit 018 - 1RHCU
3 | Cloud+ | 1 | Mohamed Ayyash | Typo, delete "f" from unit number, should read 050
4 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets.
5 | Callout | 1 | Mohamed Ayyash | Add unit name RTF
6 | Text Box | 1 | A.Jabbar Mahmood | The reported pump differential head is lower than that in the FEED D/S and the reported NPSHa is higher than that reported in the FEED D/S. Owner has not received the revised hydraulic calculations and there cannot verify the updated pump suction and discharge pressures. To be checked and confirmed.
7 | Callout | 1 | Fatema Hashem | CHANGE THE NAME OF THIS PUMP TO "1RHCU FEED BOOSTER PUMP" SO IT WILL NOT BE CONFUSED WITH PUMP 018P1001.
8 | Call-out | 1 | Mahdi Ali | Incorrect sequence number
9 | Text Box | 1 | MAK | Use the latest cover page template that is part of the Homogenization Procedure. MOC shall coordinate with JV Directorate.
10 | Callout | 2 | alexis.martinez | GENERAL: For decimal separator use dot (.) instead of coma (,)
11 | Callout | 2 | alexis.martinez | For process data in page 2, Row 20 to 24: Provide the detailed engineering work carried out to arrive at those values.
12 | Callout | 2 | alexis.martinez | On page 2, rows from 10 to 13 and 17 to 24, completed the missing information for maximum, normal and minimum cases
13 | Callout | 2 | Mohamed Ayyash | Should read 2/9. correct all pages
14 | Cloud+ | 2 | A.Jabbar Mahmood | Ensure compliance with BMPS A1. Assumed pressure drop from/to unit B.L will need to be verified during detailed engineering
15 | Call-out | 2 | Mahdi Ali | Remove space between tag and suffix. This is applicable to all sheets.
16 | Call-out | 2 | Ahmed Bucheeri | RHCU-UNIT018
17 | Callout | 4 | Adnan Alothman | Mounting of Seal Support System on Baseplate to be checked against relative standard and confirm.
18 | Text Box | 7 | Sankara | HV motors in Zone 2 areas shall be Ex-d or Ex-e type only. Refer Query T107: Typical Comment.
19 | Callout | 7 | alexis.martinez | GENERAL: Use letter "M" instead of "PM" on the pumps electric motors TAG number.
20 | Callout | 7 | alexis.martinez | On page 7 and 8 on the Service Item is "1RHCU" instead of "Crude"
21 | Call-out | 7 | Ahmed Bucheeri | RHCU BOOSTER PUMPS
22 | Text Box | 7 | Ahmed Bucheeri | X018
23 | Text Box | 7 | Ahmed Bucheeri | 18
24 | Call-out | 8 | Ahmed Bucheeri | RHCU BOOSTER PUMPS
25 | Callout | 9 | Isamu | Delete. NPSHR test already specified as witness
26 | Call-out | 9 | Ahmed Ali | add A/B
27 | Call-out | 9 | A.Jabbar Mahmood | Typo
28 | Call-out | 9 | Mahdi Ali | Use Bapco number. FEED number shall not be used.
29 | Text Box | 9 | Ahmed Bucheeri | 18