## 058-A-PFD-50001-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Julio.Aguilar | As per BAPCO letter BMP-CON-LET-00038, the pressure at ADP and RDP is 660 psig. TTSJV shall provide clarification for selecting 630 psig pressure at inlet to microscrubbers (stream 1, 058-A-PFD-50001-001-Sht 4)
2 | Callout | 1 | BD Mori | Provide reference to note 4
3 | Callout | 1 | BD Mori | As per 2/3 BAGRU PFD stream 62 this flow is 545073 lb/hr. Check and revise if required.
4 | Callout | 1 | BD Mori | As per 2/3 BAGRU PFD stream 62 this temperature is 124°F. Check and revise if required.
5 | Callout | 1 | BD Mori | As per 3 TGTU PFD stream 152 this flow is 3666.5 lb/hr. Check and revise if required.
6 | Callout | 1 | BD Mori | As per 4 TGTU PFD stream 150 this flow is 3666.5 lb/hr. Check and revise if required.
7 | Call-out | 1 | 986131 | Provide a note stating that above figures would be reviewed after the SGP Off Gas (going to refinery fuel gas) composition is finalized based on SGP alternative development and LPG saturation system is finalized.
8 | Callout | 1 | Fatema Hashem | THE LHV OF PROCESS GAS IS INCONSISTENT WITH THE SPECIFIED LHV ON THE FIRED HEATERS DATASHEETS. CHECK AND CORRECT ACCORDINGLY.
9 | Callout | 1 | Fatema Hashem | REVIEW AND CONFIRM THE STANDARD VOL FLOW OF STREAM 14 PROCESS GAS REQUIRED TO SATISFY THE FIRED DUTY PER 1RHCU UTILITY SUMMARY.
10 | Callout | 1 | Fatema Hashem | WHAT IS THE BASIS OF THIS LHV OF 889 BTU/SCF??
11 | Callout | 1 | Fatema Hashem | REVIEW THE FLOWRATE OF PROCESS GAS REQUIRED IF VAC COL NON-CONDENSABLES ARE NOT AVAILABLE. AS PER 1RHCU UTILITY SUMMARY, 20.9MMBTU/H EXTRA FIRED DUTY WILL BE REQUIRED, I.E. THE TOTAL FIRED DUTY FOR FRAC HEATERS WILL BE 65.4MMBTU/H. PRELIMINARY CHECKS INDICATE A HIGHER FLOW MAY BE REQUIRED.
12 | Callout | 1 | Fatema Hashem | REVIEW THE FLOWS OF STREAM 14. PRELIMINARY CHECKS INDICATE A HIGHER FLOW MAY BE REQUIRED TO ACHIEVE THE FIRED DUTY AS PER 1RHCU UTILITIES SUMMARY
13 | Callout | 1 | Fatema Hashem | ADD THE COMPOSITION OF ALL STREAMS, TO BE CONSISTEN WITH COMPOSITIONS PROVIDED ON FIRED HEATERS DATASHEETS