## 083-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | balagangadhar.k | N2P
2 | Text Box | 1 | balagangadhar.k | NOTE 16
3 | Callout | 1 | balagangadhar.k | This is two-way line, show bothside arrows to this line
4 | Call-out | 1 | Hasan Al Noaimi | Plant
5 | Callout | 1 | Julio.Aguilar | To be added to Note 8: Liquid nitrogen to be sent to storage as a slightly sub-cooled liquid. Mixed phase to be avoided in the liquid nitrogen transfer lines.
6 | Callout | 1 | Dowon Pyun | Note 1 & 4
7 | Text Box | 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.
8 | Callout | 1 | balagangadhar.k | Show arrow at every change in direction (typical)
9 | Callout | 1 | Robert.Kawitzki | Add font to legend
10 | Callout | 1 | balagangadhar.k | No. 3
11 | Call-out | 1 | MAK | Remove letter f
12 | Call-out | 1 | MAK | Remove letter h
13 | Callout | 1 | BD Mori | How to prevent low temperature in downstream piping and equipment? Specify if interlock is required to cut off nitrogen flow on low-low temperature. Add appropriate note to PFD.
14 | Callout | 1 | Julio.Aguilar | To be added in Note 7: This value is preliminary and shall be confirmed in later stage once the final plot plant is completed.
15 | Text Box | 1 | balagangadhar.k | Replace "NITROGEN PLANT" with "No.1 NITROGEN PLANT" at all places
16 | Callout | 1 | Salman Jaffer | This phase is EPC, do we need to retain this statament
17 | Call-out | 1 | MAK | 083 - NO. 1 NITGROGEN PLANT
18 | Call-out | 1 | MAK | Always show the border size A1
19 | Text Box | 1 | balagangadhar.k | NOTE 16
20 | Call-out | 1 | Hasan Al Noaimi | No 3 Sulphur Plant
21 | Call-out | 1 | MAK | Never use the word NEW
22 | Callout | 1 | BD Mori | Why " BY-PASS" . Review and delete word " BY-PASS " if not applicable.
23 | Callout | 1 | Dowon Pyun | This drawing is block diagram rather than PFD. Contractor to add a statement 'Package Supplier shall provide developed PFD.
24 | Callout | 1 | Syed Ahmed | Add 1HRU
25 | Callout | 1 | Salman Jaffer | Include Horton Spheres, KRU and 5CDU. Check about FCCU Flare.
26 | Call-out | 1 | Hasan Al Noaimi | LBOP
27 | Call-out | 1 | MAK | NO. 1 NITROGEN PLANT (083)
28 | Call-out | 1 | MAK | Total Sht. shall be indicated only, 001
29 | Callout | 1 | Julio.Aguilar | Add tag number as per BMPS-A8
30 | Callout | 1 | BD Mori | Add stream conditions for all the streams after the BMP Nitrogen balance is finalised and reissue the PFD for review.
31 | Text Box | 1 | balagangadhar.k | NOTE 13,15
32 | Callout | 1 | Salman Jaffer | Rename 1Flare to Refinery South Flare
33 | Callout | 1 | balagangadhar.k | US Gal (per BMPS A-1)
34 | Text Box | 1 | balagangadhar.k | NOTE 12
35 | Callout | 1 | Syed Ahmed | 076V7616A/B
36 | Text Box | 1 | balagangadhar.k | NOTE 14,15