## 088-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Sang.Hwang | i font shall be corrected. This is typical for all i fonts.
2 | Callout | 1 | Dowon Pyun | Tray numbering from bottom to top as per the section 7.6 of BMPS-A3
3 | Cloud+ | 1 | Julio.Aguilar | OPERATIONS
4 | Callout | 1 | Salman Jaffer | Based on site condition, existing tubes bypass to be retained. Please correct the PFD according the actual tie-ins provided by BAPCO
5 | Text Box | 1 | balagangadhar.k | Show New Equipment and equipment data blocks in Bold - drafting
6 | Callout | 1 | Salman Jaffer | Please refer to (PID BRA-75760 sheet 4 of 6) line No. (000-3"-P0029-C30N-N) and (BRB-228345 sheet 1 of 13 ) for stream 12D and include stream Unstabilized Naphtha to SGPs. Associated stream data have to be provided in HMB.
7 | Callout | 1 | Salman Jaffer | This is a new bypass part of scope of work. Refer to Line (088-6"-P1007-C2-Ih) and tie-ins 03L and 04L of the FEED PID BRA-75760 sheet 3 of 7
8 | Callout | 1 | Salman Jaffer | Lines which will be decommissioned post BMP to be identified and highlighted
9 | Text Box | 1 | Mahdi Ali | Unit 088 is an existing unit and JV shall officially request the native file to be sent for modifications. It is not acceptable to use the FEED PFDs as there might been some modifications to the existing PFDs. Modifications shall be clouded.
10 | Callout | 1 | balagangadhar.k | Show Arrow at every change in direction (Typical)
11 | Callout | 1 | Salman Jaffer | Indicate destination of OFF-SPEC Naphtha
12 | Text Box | 1 | Mahdi Ali | Where from did JV get this number?
13 | Text Box | 1 | Mahdi Ali | General Comments applicable to all PFDs 1. Follow the Homogenization procedure for the Off-page Connectors. 2. Modifications shall be clouded as per BMPS-A8. 3. Use latest drawing borders.
14 | Callout | 1 | balagangadhar.k | Show Air cooler symbol as per LEGEND, this line to be deleted
15 | Callout | 1 | Salman Jaffer | Delete