## 094-A-MSD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Saeed Taher | Material to be specified
2 | Text Box | 1 | MAK | General Comments applies to all MSDs: 1. Use the latest PFD border and off-page connectors that are part of the Homogenization Procedure. SOC shall coordinate with TTSJV. 2. Total Sheet to be shown as e.g. 006 on all the sheets. 3. Always use NTS for MSD scale. 4. Always use A1 for MSD border size.
3 | Text Box | 1 | Mahdi Ali | Scale: NTS Size: A1 TTL SHT: 006
4 | Callout | 1 | Salman Jaffer | Add Note 2 for this line from downstream of XV1166. This portion should be steam jacketed. Refer to steam jacketed line (094-8"-SU0108-B11-Ij) / 094-10"-S0108-B11-Ih), FEED PID BRA-227160 sheet 2 of 12. Same issue for the vent to atmosphere.
5 | Callout | 1 | Robert.Kawitzki | equipment labels as per BMPS-A8 - typ comment
6 | Text Box | 1 | MAK | General Comment: The equipment data shall be placed in alignment with the location of the equipment as possible.
7 | Text Box | 1 | Mahdi Ali | Use latest PFD border
8 | Text Box | 1 | MAK | Verify the equipment nos. with the agreed equipment list.
9 | Callout | 1 | Dowon Pyun | To be referred with project document no.
10 | Callout | 1 | Salman Jaffer | General comment: Refer to Bid Query T1099 and consider (CA’s are 1/8” for inner pipe and 1/16” for outer pipe).
11 | Callout | 1 | Saeed Taher | Material to be specified for vent line