## 094-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Always show the border size A1
2 | Call-out | 1 | Ali Abbas | connected to where?
3 | Text Box | 1 | Sang.Hwang | Equipment data block shall be completed for each item.
4 | Callout | 1 | Salman Jaffer | Equipment of this tank needs to be reviewed.
5 | Text Box | 1 | Sang.Hwang | i font shall be re-checked & corrected.
6 | Callout | 1 | balagangadhar.k | Is not possible to inject 70 psig BFW to 70 psig steam header considering drop in TV & desuperheater. Check BMPS-A1 for BFW pressure.
7 | Call-out | 1 | Ali Abbas | PFD we show TC not TEs details. Please homogenise, harmonise and standardise will all other PFDs
8 | Callout | 1 | Salman Jaffer | Please provide stream data
9 | Call-out | 1 | Ali Abbas | should be LC to ?
10 | Call-out | 1 | Ali Abbas | show arrow. General comments to all sheets and PFDs
11 | Call-out | 1 | Ali Abbas | show control loop
12 | Call-out | 1 | Ali Abbas | show line break for crossing signals
13 | Call-out | 1 | Ali Abbas | This details applicable to PFD. General comment.
14 | Text Box | 1 | Nalini Mohan | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. PFD shall be modified to incorporate the updated streams data and H&M balance
15 | Call-out | 1 | MAK | Total Sht. shall be indicated only, 007
16 | Text Box | 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.
17 | Callout | 1 | BD Mori | We understand this temperature is revised based on the stream #1 data. However, note that the tank has steam heating coil. Therefore, review this temperature in view of the steam coil.