## 098-A-PFD-00001-003-RA-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | balagangadhar.k | Show package symbol in double dotted lines
2 | Text Box | 1 | balagangadhar.k | HP STRIPPER STEAM SILENCER
3 | Text Box | 1 | balagangadhar.k | Provide the name of each package
4 | Text Box | 1 | balagangadhar.k | 098V0016
5 | Callout | 1 | BD Mori | Move this tag number here
6 | Callout | 1 | BD Mori | Consult licensor for requirement of filter on this stream
7 | Callout | 1 | BD Mori | This exchanger symbol to be changed to indicate plate and shell type exchanger. Accordingly BMPS-A-50003 to be modified.
8 | Callout | 1 | BD Mori | How to prevent carryover of adsorbent fines from PSA to hydrogen net work and ultimately to compressors? To prevent the fines carryover,PSA product filter is required.
9 | Callout | 1 | BD Mori | Move this tag number here
10 | Call-out | 1 | Hasan Al Noaimi | filter is required like V7611
11 | Call-out | 1 | Hasan Al Noaimi | to Hydrogen header
12 | Cloud+ | 1 | Jawad Alawi | Exchanger type to be revised for plate & shell
13 | Text Box | 1 | Mahdi Ali | Rotary equipment labels to be shown at the bottom of the drawing area
14 | Typewritten Text | 1 | MAK | S
15 | Typewritten Text | 1 | MAK | S
16 | Text Box | 1 | Sang.Hwang | i font shall be re-checked & corrected.
17 | Callout | 1 | Syed Ahmed | this package is compressor, indicate the compressor symbols as per BMPS-A-50003
18 | Callout | 1 | Syed Ahmed | Based on the PSA package vendor there is a likelihood of another purge gas vessel. JV shall update the PFD.
19 | Callout | 1 | Syed Ahmed | Keep this valve black as per BMPS-A-50003 Normally close for PFD only.
20 | Callout | 1 | Syed Ahmed | Don't show this valve on PFD
21 | Callout | 1 | Syed Ahmed | General comment: keep all analyzers drawing as per BMPS-A-50003 general instruments part.