## 311-A-MSD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Saeed Taher | Add : 1- Material selection to be confirmed by chemical vendor
2 | Call-out | 1 | MAK | Always show the border size A1
3 | Callout | 1 | Robert.Kawitzki | Equipment number as per BMPS-A8 7.2.5.4 - typ comment
4 | Callout | 1 | Robert.Kawitzki | Equipment number?
5 | Callout | 1 | Saeed Taher | Material to be specified for drain line US & DS the valve as per BMPS-L2
6 | Call-out | 1 | Mahdi Ali | Scale: NTS
7 | Callout | 1 | Robert.Kawitzki | Show continuation drawing number - typ comment
8 | Callout | 1 | Robert.Kawitzki | Text width and height to be as per project standard. Make arrow larger not text smaller - typ comment
9 | Call-out | 1 | MAK | Total Sht. shall be indicated only, 004
10 | Text Box | 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.
11 | Callout | 1 | Robert.Kawitzki | What is this equipment? Steam desuperheater? Equipment number required?
12 | Callout | 1 | Robert.Kawitzki | What is this? Flow control valve? Has the P&ID legend sheet been revised to reflect this?