## 341-A-PFD-00001-004-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Sameer.Ahmed | "C3/C3" & "Refinery Tank Farm (New portion)" to be included
2 | Callout | 1 | Julio.Aguilar | Consistency of Note 5 with similar Note 3 on PFD Nro. 341-A-PFD-00001-002 to be revised and updated.
3 | Text Box | 1 | Julio.Aguilar | H&MB to be updated after the air consumption revision to be done during detail engineering phase.
4 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. TTSJV to advise when the first utilities balance will be submitted for review. PFD shall be modified to incorporate the updated utilities streams data and H&M balance