## 907-A-BOD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Microsoft Word - Code 3 With Comments |  | Adel
2 | Call-out |  | Ali Abbas | General Comment: I understand this is a process design basis, I suggest to add a short paragraph regarding the scope associated with DCS graphics and line-ups modifications/new requirements for all these changes.
3 | Text Box |  | rob.urban | All connections which need to be made between existing facilities/pipelines and new pipelines have to be identified. Where will this be done and where will the tie-ins be listed? This includes verifying and taking into account the design conditions of existing facilities.
4 | Typewritten Text |  | Nabeel | (UNIT 907)
5 | Typewritten Text |  | Mohamed Ayyash | add space
6 | Arrow |  | Mohamed Ayyash
7 | Arrow |  | Mohamed Ayyash
8 | Arrow |  | Mohamed Ayyash
9 | Typewritten Text |  | Mohamed Ayyash | move back
10 | Pen |  | Peter Fagg | .
11 | Pen |  | Peter Fagg
12 | Typewritten Text |  | Peter Fagg | 380 MBPD
13 | Arrow |  | Peter Fagg
14 | Typewritten Text |  | Peter Fagg | It is the design case in the financial model
15 | Line |  | Mohamed Ayyash
16 | Line |  | Nabeel
17 | Arrow |  | Nabeel
18 | Typewritten Text |  | Nabeel | None
19 | Typewritten Text |  | Mohamed Ayyash | s
20 | Arrow |  | Mohamed Ayyash
21 | Typewritten Text |  | Peter Fagg | should nominate Sitra Tanks
22 | Arrow |  | Mohamed Ayyash
23 | Arrow |  | Mohamed Ayyash
24 | Typewritten Text |  | Mohamed Ayyash | move back
25 | Arrow |  | Nabeel
26 | Typewritten Text |  | Nabeel | Transfer
27 | Line |  | Mohamed Ayyash
28 | Arrow |  | Mohamed Ayyash
29 | Arrow |  | Mohamed Ayyash
30 | Typewritten Text |  | Mohamed Ayyash | move back
31 | Typewritten Text |  | Peter Fagg | to 56D760/741
32 | Arrow |  | Mohamed Ayyash
33 | Typewritten Text |  | Mohamed Ayyash | move back
34 | Text Box |  | Mohamed Ayyash | move back
35 | Arrow |  | Mohamed Ayyash
36 | Arrow |  | Mohamed Ayyash
37 | Typewritten Text |  | Mohamed Ayyash | s
38 | Arrow |  | Mohamed Ayyash
39 | Text Box |  | Mohamed Ayyash | move back
40 | Arrow |  | Mohamed Ayyash
41 | Arrow |  | Mohamed Ayyash
42 | Arrow |  | Mohamed Ayyash
43 | Text Box |  | Peter Fagg | need to consider C3 & C4 startup lines from Banagas
44 | Typewritten Text |  | Mohamed Ayyash | s
45 | Arrow |  | Mohamed Ayyash
46 | Text Box |  | Mohamed Ayyash | move back
47 | Arrow |  | Mohamed Ayyash
48 | Arrow |  | Mohamed Ayyash
49 | Arrow |  | Mohamed Ayyash