## 20181001_121920
Bapco Code | Rev. | Transmittal | Trans. Date | Bapco Response Code | Note
000-C-GRD-60004-001 | AP | BMP-ROC-TRE-000013 | 2018-04-06 | 3-REVIEWED WITH COMMENTS | REF: CON-BMP-TRA-010017
000-G-MRQ-60005-001 | A | BMP-ROC-TRE-000400 | 2018-08-22 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010403
000-J-MST-50001-001 | A | BMP-DIR-TRE-000147 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000331
000-L-MRQ-50021-001 | A | BMP-DIR-TRE-000065 | 2018-07-05 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000131
000-L-MRQ-50030-001 | A | BMP-DIR-TRE-000067 | 2018-07-05 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000136
000-L-MST-50001-001 | A | BMP-DIR-TRE-000146 | 2018-08-27 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-000314
000-M-MST-50001-001 | A | BMP-DIR-TRE-000142 | 2018-08-22 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000336
000-P-SYM-50001-001 | A | BMP-DIR-TRE-000056 | 2018-07-05 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-000121
000-R-STD-50002-001 | A | BMP-DIR-TRE-000138 | 2018-08-20 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000304
000-R-STD-50005-001 | A | BMP-DIR-TRE-000138 | 2018-08-20 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000304
000-R-STD-50006-001 | A | BMP-DIR-TRE-000138 | 2018-08-20 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000304
000-R-STD-50007-001 | A | BMP-DIR-TRE-000138 | 2018-08-20 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000304
000-R-STD-50008-001 | A | BMP-DIR-TRE-000138 | 2018-08-20 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-000304
005-A-EQL-55001-001 | A | BMP-SOC-TRE-000673 | 2018-08-23 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-070676
005-J-INX-50002-001 | A | BMP-ROC-TRE-000419 | 2018-08-26 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010463
010-C-GAD-10006-001 | AP | BMP-MOC-TRE-000003 | 2018-04-11 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-040002
018-A-PID-00096-001 | A | BMP-ROC-TRE-000113 | 2018-07-02 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010129
018-A-PID-00096-002 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-00096-003 | A | BMP-ROC-TRE-000113 | 2018-07-02 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010129
018-A-PID-00096-009 | A | BMP-ROC-TRE-000113 | 2018-07-02 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010129
018-A-PID-20002-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20003-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20005-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20006-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20009-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20013-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20016-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20017-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20018-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20019-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20020-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20021-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20023-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20024-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20025-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20026-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20027-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20030-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-A-PID-20036-001 | A | BMP-ROC-TRE-000112 | 2018-06-29 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010122
018-C-DAT-00036-001 | A | BMP-ROC-TRE-000344 | 2018-07-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010244
018-C-DAT-00090-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00091-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00092-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00093-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00095-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00096-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00097-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00098-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00099-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00100-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00101-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00102-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00103-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00104-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00105-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00106-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00107-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00108-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-C-DAT-00109-001 | A | BMP-ROC-TRE-000434 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010436
018-G-DAT-00033-001 | B | BMP-ROC-TRE-000403 | 2018-08-23 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010395
021-C-GAD-00001-002 | 0 | BMP-ROC-TRE-000360 | 2018-08-10 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010333
021-C-GAD-00001-003 | 0 | BMP-ROC-TRE-000360 | 2018-08-10 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010333
023-A-CAL-00003-001 | A | BMP-ROC-TRE-000407 | 2018-08-23 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-010434
023-C-DAT-00007-001 | A | BMP-ROC-TRE-000435 | 2018-08-28 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-010438
043-F-DAT-00002-001 | AP | BMP-SOC-TRE-000001 | 2018-04-09 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-070002
048-E-DAT-00005-001 | A | BMP-SOC-TRE-00231 | 2018-06-25 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-070176
050-A-CAL-55001-001 | B | BMP-MOC-TRE-000505 | 2018-08-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-040508
050-K-DAT-55006-001 | A | BMP-MOC-TRE-000066 | 2018-05-30 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-040071
050-L-INX-50001-001 | A | BMP-ROC-TRE-000415 | 2018-08-26 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-010469
050-S-BLD-55001-001 | A | BMP-MOC-TRE-000457 | 2018-08-12 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-040434
050-S-PED-55810-001 | A | BMP-MOC-TRE-000245 | 2018-07-25 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-040365
050-S-PED-55811-001 | A | BMP-MOC-TRE-000245 | 2018-07-25 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-040365
051-S-GAD-00001-001 | A | BMP-ROC-TRE-000414 | 2018-08-26 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-010458
056-A-PID-00016-001 | 4A | BMP-ROC-TRE-000120 | 2018-07-03 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010133
056-C-DAT-50001-001 | A | BMP-ROC-TRE-000432 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010439
056-J-INX-50002-001 | A | BMP-ROC-TRE-000420 | 2018-08-26 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010464
058-A-CAL-50002-001 | A | BMP-ROC-TRE-000409 | 2018-08-26 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-010432
058-A-PPN-50001-001 | A | BMP-ROC-TRE-000413 | 2018-08-26 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-010448
073-L-INX-50001-001 | A | BMP-ROC-TRE-000421 | 2018-08-26 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010472
079-A-CAL-00001-001 | A | BMP-MOC-TRE-00302 | 2018-08-19 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010340
180-L-INX-00001-001 | A | BMP-ROC-TRE-000428 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010478
371-A-BOD-50002-001 | A | BMP-ROC-TRE-000411 | 2018-08-26 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010443
371-A-PFD-50001-001 | A | BMP-ROC-TRE-000197 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010187
371-A-PFD-50001-002 | A | BMP-ROC-TRE-000197 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010187
371-A-PFD-50001-003 | A | BMP-ROC-TRE-000197 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010187
371-A-PFD-50001-004 | A | BMP-ROC-TRE-000197 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010187
371-A-PID-00001-001 | 3A | BMP-ROC-TRE-000193 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010175
371-A-PID-00027-007 | 4A | BMP-ROC-TRE-000193 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010175
371-A-PID-50001-001 | A | BMP-ROC-TRE-000193 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010175
371-A-PID-50002-001 | A | BMP-ROC-TRE-000193 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010175
371-A-PID-50003-001 | A | BMP-ROC-TRE-000193 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010175
371-G-DAT-50001-001 | A | BMP-ROC-TRE-000201 | 2018-07-24 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010196
372-A-CAL-57001-001 | B | BMP-MOC-TRE-000514 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-040516
372-C-DAT-55006-001 | A | BMP-SOC-TRE-000245 | 2018-06-26 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-070257
372-C-DAT-55007-001 | A | BMP-SOC-TRE-000245 | 2018-06-26 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-070257
907-L-INX-50001-001 | A | BMP-ROC-TRE-000427 | 2018-08-27 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-010479
930-A-PPN-00001-001 | A | BMP-ROC-TRE-000408 | 2018-08-23 | 4-NOT APPROVED | REF.: CON-BMP-TRA-010449
930-A-PPN-00001-002 | A | BMP-ROC-TRE-000408 | 2018-08-23 | 4-NOT APPROVED | REF.: CON-BMP-TRA-010449
930-A-PPN-00001-003 | A | BMP-ROC-TRE-000408 | 2018-08-23 | 4-NOT APPROVED | REF.: CON-BMP-TRA-010449
930-S-CAL-00001-001 | A | BMP-ROC-TRE-000429 | 2018-08-27 | 3-REVIEWED WITH COMMENTS | REF.: CON-BMP-TRA-010481
932-S-GAD-00001-001 | A | BMP-SOC-TRE-000665 | 2018-08-22 | 2-REVIEWED WITH MINOR COMMENTS | REF.: CON-BMP-TRA-070668