## 000-A-PRO-50009-001-RA
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | james.wright | to Add: 1. Include the "Reporting Requirements Matrix" as found in Vol. 2, Section 1.1 (Project Instructions), Para 9.20 - Regularity of Reporting & Modes of Issue. 2. For daily reporting, "to be developed with Construction Reporting mechanisms" | Noted.
2 | Stamp | david.huggins
3 | Arrow | Jeung.Kim
4 | Text Box | Jeung.Kim | Is this basis applied for procurement and construction phases? | TTSJV collect O.C.'s contribution for Engineering. For Procurement & Construction will be developed directly by JV
5 | Arrow | Jeung.Kim
6 | Arrow | Jeung.Kim
7 | Arrow | Jeung.Kim
8 | Arrow | Jeung.Kim
9 | Text Box | Jeung.Kim | How about to make to differentiate? | Direct & Indirect Manpower will be provided by Subcontractor to TTSJV
10 | Callout | james.wright | PM | Noted
11 | Callout | james.wright | Include "Actual vs planned S-curves and resource histograms" as found in Vol. 2, Section 1.1 (Project Instructions), Exhibit 1, Para 2.1, item d. Weekly Status Report, General | S-curves will be updated on weekly basis (Actual vs planned) while Resource histograms for H.O. on monthly basis, due to the fact that O.C.'s Mhrs Accounting Systems will provide Actual spent Mhrs on monthly basis
12 | Text Box | Daniella.Botta | Include 'per area and discipline (as a percentage and in a narrative form) 'as found in Section 1.1 Project Instructions, Exhibit 1. Para 2.2 Item b. Weekly Report Status, Engineering Activities | Progress figure will calculated by Discipline / WP's till Level 3 of Project Work Breakdown Structure
13 | Arrow | Daniella.Botta
14 | Callout | james.wright | Add "f. Quantities installed Table (Plan vs Actual)" | Noted. Key Qty Table installed (Plan vs Actual) will be provided
15 | Line | james.wright
16 | Callout | james.wright | "5th Calendar Day" as defined in Vol. 2, Section 1.1 (Project Instructions), Exhibit 1, Para 3. Monthly Status Report | Noted
17 | Callout | Daniella.Botta | Include Cost Status as defined in Vol. 2, Section 1.1 (Project Instructions), Exhibit 1, Para 3. Monthly Status Report | Noted
18 | Arrow | Daniella.Botta
19 | Text Box | Daniella.Botta | Include details described in Vol. 2, Section 1.1 (Project Instructions) Para 7.11 Project Milestones Status Report | Noted
20 | Arrow | Daniella.Botta
21 | Text Box | Daniella.Botta | Include item d as found in Vol. 2, Section 1.1 (Project Instructions), Exhibit 1, Para 3. Monthly Status Report, Engineering | Noted
22 | Arrow | Daniella.Botta
23 | Text Box | Daniella.Botta | Include CTN register | Noted
24 | Text Box | james.wright | a. Indexed Progress Photographs | Noted. It will be implemented as soon as Construction Works will start