## 000-A-PRO-50015-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Document Title shall be placed in the header
2 | Text Box | Page 1 | Ravi Kumar | The TQ workflow procedure shall be extended further to include which documents will be impacted by the change approval and a tracking procedure to know the referenced documents are updated
3 | Text Box | Page 1 | Stephen.Jackson | Reference also needs to be made to Annex 1, Project Instructions, in particular Para. 5 which provides obligations on the Contractor to provide details on a CTN for any impacts associated with cost, quality or schedule related to Deviations, Waivers, TQ's and Concessions.
4 | Text Box | Page 3 | Jeung.Kim | Please add "Company" in the Section 2 as it may cause confusion.
5 | Text Box | Page 3 | Stephen.Jackson | General, in the event of any conflict between this document and the Contract, the Contract will prevail.
6 | Text Box | Page 4 | Jeung.Kim | Please make a clear identification between JV, Contractor and OC as it is difficult to exactly understand who is the Contractor.
7 | Text Box | Page 4 | Jeung.Kim | Is there no deviation or waiver request other than BMPS?
8 | Text Box | Page 4 | Jeung.Kim | Suggested to delete this as no meaning of it
9 | Text Box | Page 4 | Jeung.Kim | Why does the Contractor include this Owner internal procedure in his procedure?a
10 | Text Box | Page 4 | Jeung.Kim | what kind of number of it?
11 | Text Box | Page 5 | Jeung.Kim | Strongly suggest to separate at least for each discipline.
12 | Text Box | Page 5 | Jeung.Kim | this cannot be a justification as the Contract signed without such deviation
13 | Text Box | Page 6 | Jeung.Kim | may not shall
14 | Text Box | Page 6 | Jeung.Kim | Contractor own evaluation and justification of proposed deviation by vendor has to be included in the request
15 | Callout | Page 6 | Nalini Mohan | Exceptions/deviations on particular items that have been highlighted by multiple vendors only should be formally evaluated and forwarded to Company. Individual exceptions will not be reviewed.
16 | Text Box | Page 7 | Jeung.Kim | Please add procedure for the TQ- who prepare, review and approve for which kind of clarification and query will be issued or other details
17 | Text Box | Page 13 | Mahdi Ali | Bapco document number shall be placed in the footer for all other pages
18 | Text Box | Page 13 | Jeung.Kim | Please add any cost variation(save or addition) due to waiver or deviation
19 | Callout | Page 13 | Nalini Mohan | Spell check "Discipline"
20 | Callout | Page 14 | Nalini Mohan | Conflict resolution form should be different. This form should highlight OWNER's final position only. There is no question of approve or reject
21 | Text Box | Page 17 | Mahdi Ali | Bapco document number shall be placed in the footer for all other pages
22 | Callout | Page 17 | Nalini Mohan | Query form should be different. There is no need for APPROVE/REJECT and also It need not be approved by OWNER Project Director