## 000-A-PRO-50031-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 3 | Jeung.Kim | Suggested to modify it as this procedure has to cover all E, P, C and Commissioning/start-up.
2 | Callout | Page 4 | james.wright | Include description of Software to be used (Primavera P6, Acumen Fuse, Etc)
3 | Callout | Page 4 | james.wright | Make reference to WBS issued by TTSJV
4 | Callout | Page 4 | james.wright | Add: Level 1 Project Contract Schedule
5 | Callout | Page 4 | james.wright | Add: Critical Path Network for Pre-commissioning and Commissioning (Per Exhibit 3, Para 4)
6 | Callout | Page 5 | Bernard.Grace | This is not included in the acronyms at Appendix 1
7 | Callout | Page 5 | james.wright | Add: in a logic linked
8 | Text Box | Page 5 | james.wright | Reword the entire section on Level 2 Project Summary Schedule "in line" with Contract, Vol 2, Section 1.1 Project Instructions, Para 9.5, Level 2 Summary Schedule
9 | Callout | Page 5 | james.wright | "Change to: Before the commencement of Construction Works" as per: Vol 2 Common Docs & Reqts, Exhibit 3 - Planning & Scheduling, Para 4.5 - Schedule for Construction
10 | Callout | Page 5 | james.wright | Add: 6.x - Progress Curves - Detailed breakdown including tabulation of "Progress Curves"Per Exhibit 3, Para 4.2 - Progress Curves)
11 | Callout | Page 5 | james.wright | Add: Construction Schedule by Sub-Contract (Per Exhibit 3, Item 4.5.1)
12 | Callout | Page 5 | james.wright | Add: "Contractor shall develop separate system for Precom/Comm and S/U Schedule (Per Exhibit 3, Para 4.5)
13 | Callout | Page 6 | Bernard.Grace | This will promote standard details and deliverables across the 3 design centres and mitigate rework
14 | Callout | Page 6 | Bernard.Grace | Include Factory Acceptance Tests, port/customs period
15 | Callout | Page 6 | Bernard.Grace | Tracking and Control
16 | Callout | Page 6 | james.wright | Add: The H/O
17 | Callout | Page 6 | james.wright | The Owner approved
18 | Text Box | Page 6 | james.wright | d. Owner may require any other grouping
19 | Text Box | Page 6 | Jeung.Kim | ??- what does the FAT link with Sub-contract?
20 | Callout | Page 7 | james.wright | For H/O and Construction Exhibit 3, 4.4.2 & 4.8.1
21 | Text Box | Page 7 | james.wright | d. Major Quantities for Construction (Category / type to be agreed with Owner)
22 | Callout | Page 7 | james.wright | Add: the schedules,
23 | Callout | Page 7 | james.wright | e. Construction Equipment Planning (Exhibit 3, Para 4.8, Item 4.8.8 - Construction Equipment Planning)
24 | Callout | Page 7 | james.wright | d. Complete package of schedules & documentation (Planning Dossier) per Vol 2, Sect 1.1, Para 9, Item 9.10.2
25 | Callout | Page 7 | james.wright | Add: in
26 | Callout | Page 7 | james.wright | Construction & Precomm Schedules to be completed before commencement of the Constr. works (Per. Exhibit 3, Para 4.5 - Planning & Scheduling)
27 | Callout | Page 7 | james.wright | Exhibit 3, Item 4.8.2 - Procurement Schedule (Add: The RAS dates shall be indicated against each Req / PO where the fcst date is likely to exceed the RAS date (in a remarks column)
28 | Callout | Page 7 | james.wright | Include Construction Sub-Contract Schedule (Per Exhibit 3, Item 4.8.3)
29 | Text Box | Page 7 | Jeung.Kim | Is the schedule updated for additional period?
30 | Callout | Page 8 | james.wright | (Add: as per the the agreed Progress Measurement Procedure rules of credit / work-steps)
31 | Callout | Page 8 | james.wright | Add: 6.x.x - Construction Sub-contracting Schedule (per Exhibit 3, Item 4.8.3
32 | Callout | Page 8 | james.wright | Add: Weekly
33 | Text Box | Page 8 | james.wright | Ï Mobilization/Demobilization plans including Schedules of Constr. infrastructure (TCF, Laydown, etc.)
34 | Text Box | Page 8 | james.wright | Add:
35 | Text Box | Page 8 | james.wright | Ï Construction Equipment loading chart
36 | Text Box | Page 8 | james.wright | Add:
37 | Callout | Page 9 | james.wright | 6.3.6 - Construction Equipment Planning - As per Exhibit 3, Item 4.8.8
38 | Callout | Page 9 | james.wright | 6.3.7 - Linkage between CPM activities & docs - As per Exhibit 3, Item 4.8.9
39 | Callout | Page 9 | james.wright | Add: / planned, forecast
40 | Callout | Page 9 | james.wright | Add: forecast,
41 | Text Box | Page 9 | james.wright | Ï All schedule updates from Contractor will show the following for each activity: - Current start and finish dates - Target finish date - Current float - Finish variance - OD and RD - Percent complete (Per Exhibit 3, Para 4.9 - Level 4 - Control Level Schedules)
42 | Text Box | Page 9 | james.wright | Add:
43 | Text Box | Page 9 | james.wright | Ï Level 4 Construction Schedules shall include: - 3 Week Look Ahead Schedule (to be included in weekly report) - Facilities Start-up Schedule - System Completion Schedule (Per Vol 2, Section 1.1, Para 9.9 - Level 4 Construction Schedules)
44 | Text Box | Page 9 | james.wright | Add:
45 | Callout | Page 9 | james.wright | Add: Contractor shall be responsible to bring additional Mpwr as req'd to meet the scheduled progress and to recover slippage at no cost to Owner (Per Exhibit 3, Item 4.8.7)
46 | Text Box | Page 10 | james.wright | Ï Histogram by H/O Functions (Discipline)
47 | Text Box | Page 10 | james.wright | Add:
48 | Callout | Page 10 | james.wright | List the Major types proposed.
49 | Text Box | Page 10 | Jeung.Kim | Suggested to generate the quantity curves for major bulk materials(concrete, structure, piping, cables or others) for each engineering, procurement and construction phase to show the readiness of the construction work.
50 | Text Box | Page 11 | james.wright | Ï Diagnostics and analysis will be performed using P6 and Acumen Fuse software
51 | Text Box | Page 11 | james.wright | Add:
52 | Text Box | Page 11 | james.wright | Add:
53 | Text Box | Page 11 | james.wright | Calendar considerations will also include: Ï Public Holidays / Other Holidays Ï Ramadan Ï Summer Ban Period working restrictions (Bahrain)
54 | Text Box | Page 11 | james.wright | 9.2. Resource Loading (Construction) Add in the procedure a detailed description of how resource loading will be performed and used for generation of S-Curves & Histograms for the Construction, Precomm & Commissioning elements of the detailed scheduling.
55 | Text Box | Page 11 | james.wright | Add:
56 | Text Box | Page 12 | james.wright | 9.4. Activity Coding Add in the procedure a detailed description the activity coding structure to be used in Primavera P6.
57 | Text Box | Page 12 | david.huggins | Construction Areas Contractor has proposed six Construction Areas and we assume there will be six Area Construction managers and teams at site. Owner will be organizing its team under the same structure/basis. Please add a description of how the level 3 schedule and activities will be able to be sorted by Construction Area.
58 | Text Box | Page 14 | Mahdi Ali | Include CPM