## 000-A-PRO-50039-001-RA-CS
ID N° | ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | 1 | Subject |  | Author | Comments |  | N
2 | 2 | Stamp |  | Harshad.K.Patel |  |  | N
3 | 3 | Arrow |  | Mohamed Ayyash |  |  | N
4 | 4 | Arrow |  | Mohamed Ayyash |  |  | N
5 | 5 | Arrow |  | Mohamed Ayyash |  |  | N
6 | 6 | Arrow |  | Mohamed Ayyash |  |  | N
7 | 7 | Typewritten Text |  | Mohamed Ayyash | Remove dots from all sub numbers | Each dot after sub number was removed. | Y
8 | 8 | Text Box |  | Mahdi Ali | Inconsistent naming in other procedures. TTSJV has been used. | The words of "JV CONTRACTORS" were replaced with TTSJV. | Y
9 | 9 | Strikethrough |  | Mahdi Ali |  |  | N
10 | 10 | Strikethrough |  | Mahdi Ali |  |  | N
11 | 11 | Text Box |  | Mahdi Ali | To be consistent, OWNER shall be used | The word of "Client" was replaced with OWNER. | Y
12 | 12 | Arrow |  | Jeung.Kim |  |  | N
13 | 13 | Text Box |  | Jeung.Kim | Instructed what? Please modify the these statements to fit the purpose. | The statements were modified. | Y
14 | 14 | Rectangle |  | Jeung.Kim |  |  | N
15 | 15 | Call-out |  | Jawad Alawi | live | The typo was corrected to "Live" from "Life" | Y
16 | 16 | Arrow |  | Jeung.Kim |  |  | N
17 | 17 | Text Box |  | Jeung.Kim | Please add this in the reference list in below paragraph 1.6. | The acronym of "QMS" is already in the section 1.1, but additionally mentioned in paragraph 1.6. | Y
18 | 18 | Arrow |  | Jeung.Kim |  |  | N
19 | 19 | Arrow |  | Jeung.Kim |  |  | N
20 | 20 | Text Box |  | Jeung.Kim | Are the Procurement and Construction teams located for each JV Contractor? | While some of them are stayin at JV in Rome, some of them are working at OC. However, JV org. chart and OC org. chart were replaced with one integrated organization chart focusing on quality function for paragraph 3.2 quality organization to remove confusing. | Y
21 | 21 | Callout |  | Harshad.K.Patel | Overall OC organization chart provided by TTSJV do not show PQM position for each OC. | PQM is shown in each OC organization chart instead. However, JV org. chart and OC org. chart were replaced with one integrated organization chart focusing on quality function for paragraph 3.2 quality organization to remove confusing. | Y
22 | 22 | Highlight |  | Mahdi Ali |  |  | N
23 | 23 | Highlight |  | Mahdi Ali |  |  | N
24 | 24 | Highlight |  | Mahdi Ali |  |  | N
25 | 25 | Text Box |  | Mahdi Ali | TTSJV to be consistent in naming | The words of "JV CONTRACTORS" were replaced with TTSJV. | Y
26 | 26 | Typewritten Text |  | Mohamed Ayyash | add space | The space beween paragraphs was added. | Y
27 | 27 | Arrow |  | Mohamed Ayyash |  |  | N
28 | 28 | Cloud |  | Mahdi Ali |  |  | N
29 | 29 | Callout |  | Nalini Mohan | Irrespective of scope of work, subcontractors documents should be reviewed by JV before incorporating in the work. | All documents submitted by subcontractors will be reviewed by JV. The sentence was intended that subcontractors will make their documents depending on their scope of work. The sentence was modified to clearly make the intention above. | Y
30 | 30 | Arrow |  | Mahdi Ali |  | It was located in native file, but mislocated in PDF file. It was corrected. | N
31 | 31 | Callout |  | Raj | Owner need to be part of the Quality Audit team as described in the Bidder's Bid Proposal. | The new setence was added for that. | Y
32 | 32 | Callout |  | Raj | This Lessons Learnt para needs to be more specific and elaborate. Provide more specifics on the creation of a LL register from previous projects from 3 EPC partners and how they will be implemented on BMP. | The setence was added by reflecting the following. The LL register is maintained by each OC and the status will be collected to JV. | Y
33 | 33 | Call-out |  | Ali Abbas | Specific lessons learn for multi EPC Contractors project to be discussed and considered to ensure it is covered in this document. | The sentence was modified and added by reflecting the following. VE and execution plan is done by considering the LL. | Y
34 | 34 | Arrow |  | Jeung.Kim |  |  | N
35 | 35 | Arrow |  | Jeung.Kim |  |  | N
36 | 36 | Text Box |  | Jeung.Kim | Please provide these refereneces. | The references were added to the sentence. | Y
37 | 37 | Callout |  | Nalini Mohan | How does "project direction" ensure org interfaces? Not clear. Elaborate this imp. apsect | The sentences were replaced with new ones. | Y
38 | 38 | Arrow |  | Mahdi Ali |  |  | N
39 | 39 | Text Box |  | Mahdi Ali | How? | The verification methods are added to the sentence. | Y
40 | 40 | Text Box |  | Mahdi Ali | Which software? | Most of them are in-house developed spread sheets for engineering calculations. The sentence was supplemented. | Y
41 | 41 | Highlight |  | Mahdi Ali |  |  | N
42 | 42 | Text Box |  | Mahdi Ali | TTSJV to ensure that cross referencing made to those documents are tracked and removed. | The sentence was added for that. | Y
43 | 43 | Text Box |  | Mahdi Ali | Suggest to add the AFR template in the appendix for reference. | The AFR template will be included in th AFR procedure. The sentence was added for that. | Y
44 | 44 | Callout |  | Raj | Add wordings that any new vendor (not in AVL) can only be added with agreement from Owner. | The sentence was added for that. | Y
45 | 45 | Call-out |  | Ali Abbas | Need to address K.O meeting with vendor on critical equipment and Owner involvement. | The sentence was added for the kick-off-meeting. The OWNER's attendance is additionally mentioned in para. 6.7.2. | Y
46 | 46 | Call-out |  | Jawad Alawi | Typo: BMPS | It was corrected. | Y
47 | 47 | Callout |  | Nalini Mohan | OWNER shall be consulted regarding disposition of NCRs | The sentence was added for that. | Y
48 | 48 | Callout |  | Nalini Mohan | Intent is not clear. Please elaborate | The paragraph was rewritten for clear intention. | Y