## 000-A-SCH-50001-001-R0-CS
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Sankara | This document cannot be meaningfully reviewed in absence of a clear definition of the work packages. e.g. WPA, WPB etc. | Agreed, WBS has issued 16-Mar and revised schedule is aligned to issued WBS | Y
2 | Callout | david.huggins | Please note that all comments made on this document shall be considered and discussed with Owner's Project Control team for next issue of the 90 Day Starter schedule | Agreed, We had had meeting on it with PMC | Y
3 | Stamp | david.huggins
4 | Text Box | Harshad.K.Patel | Not all Execution Plans included (e.g. Engineering Management, Quality Management, Interface Management etc.) | Added | Y
5 | Callout | Harshad.K.Patel | Show weekends & Holidays | Agreed, Holydays are Color marked | Y
6 | Text Box | Jeung.Kim | Also HSE Plan missed | Added | Y
7 | Rectangle | Jeung.Kim
8 | Arrow | Jeung.Kim
9 | Text Box | Jeung.Kim | Seem incomplete or missing some words | Reflected, revised one has no missing words | Y
10 | Arrow | Jeung.Kim
11 | Text Box | Jeung.Kim | IFR | JVD decided to issue MDS as issue for inquiry | N
12 | Arrow | Daniella.Botta
13 | Text Box | Daniella.Botta | Project controls and procurement specific procedures missing | CDRL has not finished, and will be included in next updation | N
14 | Text Box | Daniella.Botta | Detailed training plan described in annex 12 exhibit F is missing | Added | Y
15 | Text Box | Daniella.Botta | Knowledge Transfer, Learning and Training Program described in annex 12 exhibit F is missing | Added | Y
16 | Text Box | Daniella.Botta | Organization procedure of the supply of Goods, inspection of Goods, follow-up and dispatching of Goods is missing | CDRL has not finished, and will be included in next updation | N
17 | Arrow | Daniella.Botta
18 | Text Box | Daniella.Botta | Due date according to contract is March 28, 30 days after ED | Reflected | Y
19 | Arrow | Daniella.Botta
20 | Text Box | Daniella.Botta | Due date according to contract is March 12, 14 days after ED | Reflected | Y
21 | Arrow | Daniella.Botta
22 | Text Box | Daniella.Botta | Due date according to contract is March 28, 30 days after ED | Divided to Planning and Scheduling Procedure, Work Breakdown Structure Project Reporting Procedure Progress Measuring and Milestone Certificate Procedure and the plan date has reflected | Y
23 | Text Box | Daniella.Botta | Activity missing for level 3/4 and onward weight factors for home office activites, due date march 26, 28 days after ED | Level 3 weight will be included in next issue of WBS | Y
24 | Arrow | Daniella.Botta
25 | Text Box | Daniella.Botta | due date according to contract is march 26, 28 days after ED | Reflected | Y
26 | Arrow | Daniella.Botta
27 | Text Box | Daniella.Botta | Due date according to contract is march 12, 14 days after ED | Reflected | Y
28 | Arrow | Daniella.Botta
29 | Text Box | Daniella.Botta | HSE procedure is missing | Including Project HSSE Plan | Y
30 | Text Box | Daniella.Botta | Activity for test plans missing | Added (QA QC/Inspection and Expediting Requirements for Vendors) | Y
31 | Text Box | Daniella.Botta | Activity missing for submittal of procedures to implement and maintain a complete control system the receipt, inspection, protection, preservation, care and custody, issuance out and inventories of all Goods consigned to Site or other areas of the project | Will be reflected in Level 3 Schedule | N
32 | Arrow | Daniella.Botta
33 | Text Box | Daniella.Botta | Clarify | Level 2 Schedule is under discussion internally and will be issued | Y
34 | Arrow | Jeung.Kim
35 | Text Box | Jeung.Kim | Please use English! | Agreed | Y
36 | Arrow | Jeung.Kim
37 | Text Box | Jeung.Kim | General comment: The issue of MDS and MR before issuing of their related precedent process design will be reviewed only for LLI or schedule critical items under condition that the design parameter related with process design will be verified before placing purchase order. All other items will be issued with engineering logical sequence. | All precedend process design deliverables are issued internally for MDS/MR preparation in full compliance with engineering logical sequence | N
38 | Arrow | Jeung.Kim
39 | Text Box | Jeung.Kim | If it is piping material class specification, it should be issued after first issue of P&ID. | Delete, TTSJV and client has decided to update BMPS instead of Specification issue | Y
40 | Callout | Harshad.K.Patel | NO instrumentation related deliverables included for any WPs - Please confirm. | Confirmed | Y
41 | Callout | rob.urban | PFD issue not realistic considering changes in RHCU | Issued in line with changes | Y
42 | Arrow | Jeung.Kim
43 | Text Box | Jeung.Kim | What is tthe definition of these WBS, WPB, C, D, E...? | Added WP with Definition | Y
44 | Arrow | Jeung.Kim
45 | Text Box | Jeung.Kim | Definition? | Issue for Execution | Y
46 | Callout | rob.urban
47 | Callout | rob.urban | Schedule is shown as bars where it can not been seen when a document is issued. For instance issue of equipment list or PFD's IBD should be one date not a period | Bar is envelop of start/finish date | N
48 | Text Box | Jeung.Kim | General Comments: 1. Are all these items LLI or schedule Critical items? Except LLI and Critical items, mechanical Data sheet and Material Requisition have to be issued after precedent process design is completed and reviewed by Client. Also the LLI and Schedule Critical items have to be confirmed its criticality in the schedule. 2. Is the issue of both MDS and MR in the same time agreed with Client? Is that only for LLI and Critical items? Otherwise it has to be agreed with Client for its procedure. | 1. All precedend process design deliverables are issued internally for MDS/MR preparation in full compliance with engineering logical sequence 2. MR ap and MDS issued in the same time for LLI and Critical items. For non-critical items, normal procedure has reflected LLI items are specially indicated in activity description and highlighted in bold | N
49 | Callout | james.wright | FS positive lags need to be avoided. They do not allow for true analysis of float. Remove where possible and add activities with FS Zero positive lag relationships. Note: For the level 3 Master Schedule "no" FS positive lags will be accepted | No FS relation with positive lags, for that quotation receive has added | Y
50 | Text Box | Robert.Kawitzki | Timing for Piping Spec and OA Plot Plan seems to be too tight | Delete, TTSJV and client has decided to update BMPS instead of Specification issue | Y
51 | Arrow | Jeung.Kim
52 | Text Box | Jeung.Kim | Does this finish date mean the first issue date? | It means WP 0 Common. However engineering plan sheet will be removed | Y