## 000-A-SCH-50002-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 3 | Nalini Mohan | Activity description is not clear
2 | Call-out | 2 | Abdul Rahim | Can not RFSU all arms togther
3 | Call-out | 3 | Ali Abbas | DCS/ESD and other PCSs PO is not listed
4 | Call-out | 3 | Ali Abbas | HGU?
5 | Call-out | 4 | Ali Abbas | HGU?
6 | Callout | 3 | Nalini Mohan | Nitrogen Package was identified as LLI/Critical Item. Accordingly PO commitment date should be advanced
7 | Call-out | 2 | Ali Abbas | Please note that Sitra/Wharf PLC upgrade to DCS is critical activity considering that all graphics, line up logics and control to be re-build, tested and commissioned without impacting Sitra/Wharf operation and ready prior to loading arm RFSU.
8 | Call-out | 3 | Edgardo | The work on the jetty / wharf will be on staggered schedule, i.e, the works on either Berths 1&3, Berths 2&4, Berth 5, & Berth 6 shall be completed before works on the other berths can be started. Hence, it is necessary that the loading arms (Refer activity WP0PM10088) should be delivered and available at site for installation during the scheduled works on each berth.
9 | Call-out | 3 | Ali Abbas | What about other WPs.