## 000-C-GRD-60005-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 9 | Ali Abbas | Instrument Nozzle location shall be finalized based on 1. take into consideration residence time/range based on criteria specified in BMPS-A3, 2. post Hazop 3 completion, 3. based on type of level measurement selected i.e. DS/GWR/Normal DP tagging etc. and 4. based on installation type, refer to BMPS Standard and Typical drawings under J. This a general comments that needs to be addressed to all OCs.
2 | Callout | 3 | Bernard.Grace | It shall be the Contractor’s (and Supplier’s / Subcontractor’s) responsibility to bring all conflicts and deviations to the Owner’s attention in a timely manner and request a ruling interpretation or a resolution in writing. Refer to Project Specification No. BMPS-A2 (Specifications, Codes and Standards) for guidelines on how to manage conflicts and deviations.
3 | Callout | 11 | Fatema Hashem | GRATING VORTEX BREAKERS AT CHIMNEY TRAYS DRAW-OFFS ARE MISSING FROM THIS TABLE. ADD WHERE APPROPRIATE
4 | Callout | 11 | Fatema Hashem | NUMBER THE CHIMNEY TRAYS PER BAPCO STANDARD. APPLICABLE TO ALL TRAYS
5 | Callout | 13 | Fatema Hashem | DRAW-OFF PIPE AT NOZZLE #21 IS MISSING FROM THIS TABLE. ADD WHERE APPROPRIATE.
6 | Call-out | 2 | Mahdi Ali | This is not part of the Table of Content. Reformat the text
7 | Call-out | 9 | Mahdi Ali | Technip or TTSJV?
8 | Call-out | 8 | Rashed Almudahka | Confirm wind design is in compliance to BMPS-A1