## 000-C-ITP-70001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | Typo, Should read No. (apply to all sheets. | Noted, will be implemented | Y
2 | Callout | 1 | Mohamed Ayyash | This is a 4 page document. Need to correct | Noted, will be implemented | Y
3 | Callout | 1 | Mohamed Ayyash | Should read "BAPCO MODERNIZATION PROGRAM " to be consistent | Noted, will be implemented | Y
4 | Text Box | 3 | Mohamed Ayyash | This page has no heading. Need to correct | Noted, will be implemented | Y
5 | Callout | 3 | Yousif Ahmadi | NDE after Hydrostatic Test. Add per inspection level 1. H 2. H 3. W | Noted, will be implemented | Y
6 | Callout | 4 | Yousif Ahmadi | Add BASE METAL WELDING CONSUMABLES section | Not applicable. Contractual form BMPS-C-50115 does not require nor to implement the requirements of Base Materials on the Inspection Checklist neither of Welding Consumables. Welding Consumables will be therefore tested as required by Project Specifications and certificates will be according to EN 10204. | N
7 | Callout | 4 | Yousif Ahmadi | Add: FERRITE TESTING (where applicable) "R" | This paragraph applies to Base Material and therefore this comment is considered not applicable. Please, let us know the reference from Project Specifications where Ferrite Testing on the Base Material (even when clad) is required | N
8 | Callout | 4 | Yousif Ahmadi | Add: FERRITE TESTING (where applicable) "R" | This paragraph applies to Base Material and therefore this comment is considered not applicable. Please, let us know the reference from Project Specifications where Ferrite Testing on the Base Material (even when clad) is required | N
9 | Callout | 4 | Yousif Ahmadi | Missing: is it for shell plate. Check and confirm | Noted, will be implemented | Y