## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | bapco-user | Change TR to CONTRACOR | Noted. It will be implemented in revision A | Y
2 | Call-out | bapco-user | change TR to CONTRACTOR | Noted. It will be implemented in revision A | Y
3 | Call-out | bapco-user | Add: Shipment | Noted. It will be implemented in revision A | Y
4 | Typewritten Text | Mohamed Ayyash | move back | Noted. It will be implemented in revision A | Y
5 | Callout | Mohamed Ayyash | suggest to use numbering for clearity | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables. | N
6 | Call-out | 986131 | ADD: Levelness check for all tray/packing support rings. | This issue is included in visual and tolerances check | N
7 | Text Box | Adnan Alothman | Correct Format of Page 3 | Page 3 is the continuity of page 2 (the same Excel page), this is the reason why it has no format | N