## BAPCO DOC. CODE-REV-CS
Date: | 2018-05-07 | Answers to Doc. No.: |  | 000-C-MRQ-70004-001-RAP-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all pages | Agreed, this typo has already been corrected and updated. | Y
2 | Text Box | 2 | Mahdi Ali | equipment tag shall be as per BMPS-A8 | Agreed, the equipment tags have already been corrected and updated as per BMPS-A8. | Y
3 | Callout | 2 | Adnan Alothman | Correct equipment number to be 019V0010 | Agreed, equipment number has already corrected as per new Tag. | Y
4 | Callout | 2 | Adnan Alothman | Add BMPS-A5 to the Spec. list | Agreed, that specification has been included to Spec. List. | Y
5 | Text Box | 3 | Hasan Asad | BMPS-S12 | Agreed, that specification has been included to Spec. List. | Y