## 000-C-SOW-60005-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 3 | Rashed Almudahka | List of documents shall be in compliance with BMPS-C-50114
2 | Call-out | 3 | Rashed Almudahka | ADD (GA drawings) to the list