## 000-E-GRD-70001-001
ID Nº | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp |  |  |  |  | -
2 | Text Box |  | Raj | Owner has reviewed and commented on the MR package submitted on Contractor's request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3. |  | -
3 | Call-out |  | Ali Abbas |  |  | -
4 | Call-out |  | Ali Abbas |  |  | -
5 | Call-out |  | Ali Abbas |  |  | -
6 | Cloud+ |  | A.Jabbar Mahmood | Does it mean "Engineering, Procurement and Construction" and what is the relevance of keeping here? Clarify | Removed EPC stands for "Engineering, Procurement and Construction" | Y
7 | Cloud+ |  | A.Jabbar Mahmood | Design Pressures of E0003/0005/0008/0012/0062/0072/0074 are different than those in the FEED D/S. Are they based on updated hydraulic calculations? CLG shall be notified. | Some design pressure values had been updated according to process hydraulic calculations, stated within the MDS (Mechanical Data Sheets) CLG had also been notified by means of MOC-JVD-TCQ-000007. | -
8 | Cloud+ |  | A.Jabbar Mahmood |  |  | -
9 | Cloud+ |  | A.Jabbar Mahmood |  |  | -
10 | Cloud+ |  | A.Jabbar Mahmood | CLGG |  | -
11 | Cloud+ |  | A.Jabbar Mahmood |  |  | -
12 | Tex Box |  | Hasan Asad | Two options shall be provided for HP Heat Exchangers - DEU Type and Modified DEU. It is the Owner responsibility to select between the two types. | HP Heat Exchangers are licensed by CLG, so that, document EXH-SU-4764-A.1 applies as follows: 1) Maximum Differential Pressures between sides < 650 psi àTEMA Type: Modified DEU àDifferential Pressure configuration à "A" Style as per EXH-SU-4764-A.1 2) Maximum Differential Pressures between sides >= 650 psi à TEMA Type: DEU à "B" Style as per EXH-SU-4764-A.1, or equivalent design such as TR Prosposal stated in Technical Query Document MOC-JVD-TCQ-000007, pending to be replied by CLG to the Directorate JVD. | MOC is waiting for CLG reply to Technical Query Document MOC-JVD-TCQ-000007
13 | Call-out |  | bapco-user | (N/A) | Updated | Y
14 | Text Box |  | Hasan Asad | The Supplier/EPC shall provide LCCA to support the 2-Year Operating Spares selection. | N/A | -
15 | Call-out |  | bapco-user | Capital Spares is Not Applicable, hence the attachment 1 needs to be removed. | Removed | Y
16 | Call-out |  | Hasan Al Noaimi | No 3 Sulphur Plant | N/A since the Attachment 1 "CAPITAL SPARES" had been removed. | -
17 | Text Box |  | Hasan Asad | This MR is for HP Heat Exchanger, the below list is not applicable. Capital spares for HP Heat Exchanger will be selected basis exchanger design selection. | Attachment 1 "CAPITAL SPARES" had been removed as required. | Y
18 | Call-out |  | Hasan Al Noaimi | Complete set is warehouse spare. | N/A since the Attachment 1 "CAPITAL SPARES" had been removed. | -