## 000-E-ITP-80007-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | Page 1 | Dowon Pyun | Criticality rating is directly affected the inspection level thus this work shall be done in advance to the decision of inspection level
2 | Text Box | Page 2 | Sankara | Variable
3 | Callout | Page 2 | Saeed Taher | Add C for contractor all pages
4 | Callout | Page 2 | Saeed Taher | Add O for owner all pages
5 | Callout | Page 2 | Saeed Taher | Owner inspection requirements to be finalized during the ITP finalization with the vendor
6 | Callout | Page 2 | Saeed Taher | Add WPS & PQR for all welded equipment - BMPS-B1
7 | Text Box | Page 2 | Hasan Asad | SAT for entire back machinery for equipment and structure vibration level.
8 | Callout | Page 4 | Saeed Taher | Instruments
9 | Callout | Page 4 | Dowon Pyun | Contractor to recheck all components of type in this ITP
10 | Callout | Page 5 | Saeed Taher | Electric Motors and Various Speed
11 | Callout | Page 6 | Dowon Pyun | Activities are not applicable to bundle & headers