## 000-E-SOW-80007-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 2 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
2 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
3 | Callout | Page 4 | BD Mori | FR | 'FI' is defined at BMPS-E-50206 (AIR COOLED HEAT EXCHANGERS - VENDOR DRAWINGS AND DATA REQUIREMENTS) | N
4 | Callout | Page 4 | BD Mori | FR | 'FI' is defined at BMPS-E-50206 (AIR COOLED HEAT EXCHANGERS - VENDOR DRAWINGS AND DATA REQUIREMENTS) | N
5 | Callout | Page 4 | Sameer.Ahmed | How about the vendor drawings which shall be provided with the proposal? This needs to be mentioned under a separate column in this table and identify which document to be provided at the proposal stage. | The information, documents and drawings which shall be provided at vendor's quotation have been separately included at the 000-E-GRD-80007-001 para.9. QUOTATION INFORMATION | N
6 | Cloud+ | Page 4 | Sameer.Ahmed | Change to "arrangement" | This is the defined name of the program 'SP materials' | N
7 | Callout | Page 4 | Sameer.Ahmed | Add: "Tube bundle construction drawing" FR | This is not exist at the program 'SP materials', and will be included at A1109 Detailed dwgs. | N
8 | Callout | Page 4 | Sameer.Ahmed | Add: "Body flange tightening specification" FR | This is not exist at the program 'SP materials', and will be included at A1109 Detailed dwgs. | N
9 | Callout | Page 4 | Nalini Mohan | FR | 'FI' is defined at BMPS-E-50206 (AIR COOLED HEAT EXCHANGERS - VENDOR DRAWINGS AND DATA REQUIREMENTS) | N
10 | Call-out | Page 5 | Ebrahim | asset and | This is not exist at the program 'SP materials', and will be clarified with vendor during TBE stage. | N
11 | Text Box | Page 5 | Sankara | Typical Comment applicable for all MRs: For LV Motors, Vendor Data Requirements as per BMPS-P-50645 shall be ensured. | This part 'DOCUMENTS AND DRAWINGS SUPPLY' has been made from BMPS-E-50206 (AIR COOLED HEAT EXCHANGERS - VENDOR DRAWINGS AND DATA REQUIREMENTS). The major informations at BMPS-P-50645 are already included, and others will be included at Operation and maintenance manuals. | N
12 | Text Box | Page 5 | Nalini Mohan | Add Safety Instruction Sheet (SIS) Add Asset Information Sheets for all equipment | This is not exist at the program 'SP materials', and will be clarified with vendor during TBE stage. | N
13 | Text Box | Page 6 | Hasan Asad | Requirement of LCCA for 20 years - per bank | Need clarification of this comment. | N