## 000-F-GRD-70002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | Yousif Ahmedi | 7CDU/7VDU
2 | Callout |  | alexis.martinez | Correct the TAG numbers. The Atmospheric Column Heater is 010F0001 and the the Vacuum Column Heater is 011F0001
| Call-out |  | Ahmed Marhoon | General Instrumentation Comments applicable to fired heaters: 1. Add all applicable BMPSs such as BMPS-J33/J1/J3/J4/J5/J6/J14/J10/J15. 2. Instrument data sheets, hook ups etc. to be provided per project specs and to be developed in SPI format. 3. All BMPS standard and typical drawings to be provided to vendor. 4. Note to be added that all heaters to have access ladder and platform for all 4 inch nozzles in the stack used for PEMPS or CEMS. However, nozzle location to be coordinated with the PEMS/CEMS vendors. 5. Oxygen/CO quoted to be corrected to Oxygen/Combustible. 6. For damper actuator, I/P is specified, as a standard project requirement; the actuator shall be fitted with a smart positioner as per spec and not I/P transducer. 7. It is stated that UPS is 220. The UPS power is 110V and not 220V. 8. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement in case ID or FD fans are used in particular to HP Boilers. 9. Ensure instruments are supplied from AVL of BMP. 10.Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. Relevant sections of the transmittal, including data sheets, issued for the furnaces to be updated accordingly.
| Re: Call-out |  | Ali Abbas
3 | Text Box |  | Raj | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
| Stamp |  | Raj
4 | Callout |  | alexis.martinez | Use 7CDU and 7VDU instead of CDU and VDU. This applies for all documents
5 | Callout |  | alexis.martinez | Include a note to mention that the equipment TAG number to be confirmed
| Call-out |  | Ali Abbas
| Pen |  | Ali Abbas | .
| Pen |  | Ali Abbas | . .
| Pen |  | Ali Abbas | . . . .
| Call-out |  | Ali Abbas
6 | Callout |  | Ahmed Ali | decoking process
7 | Call-out |  | Hasan Al Noaimi | Decoking will not be a thermal process. It will be DDT
8 | Call-out |  | Hasan Al Noaimi | low NOx burner FAT
9 | Text Box |  | Hasan Asad | Add: and equipment such as ID & FD Fan.
| Arrow |  | Hasan Asad
10 | Call-out |  | 986131 | 7VDU shutdown with 7CDU in operating at normal and turn-down case to be checked.
11 | Call-out |  | 986131 | FD Fan operating curves
12 | Call-out |  | 986131 | ID Fan Operating curves
13 | Call-out |  | Hasan Al Noaimi | PIMS connections as per ESIA
14 | Call-out |  | Hasan Al Noaimi | what about spare?
| Callout |  | Sameer Foujdar | Provision for on-line APH cleaning to be provided.
15 | Callout |  | Ahmed Ali | typo mistake and
16 | Text Box |  | Hasan Asad | Detailed design shall be reviewed and agreed - Double seat with preservation strategy
| Cloud |  | Hasan Asad
| Arrow |  | Hasan Asad
17 | Call-out |  | Hasan Al Noaimi | PEMS in the spec
18 | Call-out |  | Hasan Al Noaimi | delete if any. it has to be provided as per spec.
19 | Call-out |  | Hasan Al Noaimi | analysers in each cell
20 | Call-out |  | Jawad Alawi | add: or where metal skin point temp <350F with a risk of acid condensation
21 | Text Box |  | Sankara | UPS Power available for the project is at 110 V AC ( Typical)
| Arrow |  | Sankara
| Arrow |  | Sankara
22 | Text Box |  | Sankara | Include HAC Drawings without which correct electrical equipment cannot be selected / offered.
23 | Call-out |  | Tapas | Include the code: API RP 556 - Instrumentation, Control, and Protective Systems for Gas Fired Heaters
24 | Text Box |  | Ahmed Ali | to be changed to F0001
25 | Text Box |  | Ahmed Ali | to be changed to F0001
26 | Callout |  | alexis.martinez | The TAG number is 011F0001 and 010F0001. These TAG numbers to be confirmed.
| Arrow |  | alexis.martinez
27 | Callout |  | alexis.martinez | The re is a discrepancy with the 7CDU plot plan where the Air Pre-Heater Package is located next to 7CDU Atmospheric Column Heater.
28 | Callout |  | alexis.martinez | Change the heater description to "Atmospheric Column Heater"
29 | Text Box |  | Hasan Asad | Add: with maintenance work instruction.
30 | Text Box |  | Hasan Asad | Add: Detailed Rigging Study shall be provided.
31 | Text Box |  | Sankara | Attach BMPS-P1, P2 to this MR, which are currently found missing
| Arrow |  | Sankara
32 | Text Box |  | Sankara | Query T107: Frameproof type (Ex-d) or Increased Safety (Ex-e) for HV motors. Non-sparking (Ex-n) for LV motors.
33 | Text Box |  | Sankara | Ex-p HV motors are not acceptable
34 | Text Box |  | Hasan Asad | Basis operation scenario, loosing the FD & ID Fans will force the heater to shutdown. Hence, capital spare consist of rotor element and electric motor shall be provided due to asset criticality.
35 | Call-out |  | 986131 | Special Operation Case: 7CDU operating (either normal or turn down) and 7VDU shutdown
36 | Call-out |  | Hasan Al Noaimi | is smoke test required?
37 | Callout |  | Sameer Foujdar | if included APH on-line cleaning activity to be included and a procedure to be provided.
38 | Text Box |  | Ahmed Ali | 4.5.2 10F0001 normal operation while 11F0001 is Shutdown
39 | Call-out |  | Hasan Al Noaimi | Vacuum Heater Sd while the CDU is on line
40 | Callout |  | Ahmed Ali | decoking
41 | Call-out |  | 986131 | what is the difference between 2.3 and 2.4.
42 | Call-out |  | 986131 | Pilot Gas Shutdown