## 000-F-ITP-70002-001-RAP
ID N° | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
| Stamp | Raj
| Line | Ebrahim
| Line | Ebrahim
1 | Call-out | Ebrahim | High | Updated | Y
2 | Callout | Yousif Ahmedi | Include Pre-shipping inspection Section | Updated and included in final test | Y
3 | Callout | Yousif Ahmedi | Typo error: Subject | Updated | Y
4 | Callout | Yousif Ahmedi | Change R to W | Updated | Y
5 | Call-out | Yousif Ahmedi | Add: Weld Map | Updated | Y
6 | Callout | Yousif Ahmedi | Typo error and missing information: Subject to heat treatment during fabrication (if any) | Revised | Y
7 | Callout | Yousif Ahmedi
8 | Callout | Yousif Ahmedi | Refractory curing & Dry out | Included | Y
9 | Callout | Yousif Ahmedi | R | Included | Y
10 | Callout | Yousif Ahmedi | /Test (Holiday test) | Included | Y
| Line | Ebrahim
11 | Call-out | Ebrahim | High (Typical) | Updated | Y
12 | Call-out | Ebrahim | High (Typical) | Updated | Y
| Line | Ebrahim