## 000-K-ITP-70002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Gmarini | AP
2 | Text Box | 1 | Gmarini | AP
3 | Cloud+ | 1 | Yousif Ahmadi | Total Pages are 21 and not 18
4 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all sheets
5 | Text Box | 1 | Ahmed Marhoon | Inspection and Test Plan to include the participation of the client in accordance with the BMP agreed procedures. Loop testing plan to be detailed. Tests related to instrumentation, control and safety to comply with the BMPS J series specifications/instructions. As a minimum, the relevant Checklist as agreed for the BMP shall be referenced in the ITP. For example, BMPS-K-50411 is applicable for the Centrifugal Compressors and Oil Systems and BMPS-K-50415 for the Special Purpose Steam Turbines. This is a typical comment for all ITPs.
6 | Callout | 1 | Yousif Ahmadi | Change Technip Italy to TR
7 | Callout | 2 | Yousif Ahmadi | Add to before fabrication: WPS/ PQR/ weld map "R"
8 | Callout | 2 | Yousif Ahmadi | Add: Pre-Shipping inspection Stage
9 | Text Box | 2 | Hasan Asad | Requirement of Complete unit test shall be included. It is understandable that lube/control oil system will not be available but shop system can be used instead.
10 | Cloud+ | 4 | Mohamed Ayyash | This page has no heading !?
11 | Cloud+ | 5 | Mohamed Ayyash | This page has no heading !?
12 | Cloud+ | 6 | Mohamed Ayyash | This is page 6/21 and not 4/18. Correct all page numbers that follow.
13 | Cloud+ | 6 | Mohamed Ayyash | Overlap. Move to next page to correct
14 | Text Box | 7 | Hasan Asad | Overspeed trip test shall include mechanical and electronic.
15 | Cloud+ | 7 | Mohamed Ayyash | This page has no heading !?
16 | Callout | 8 | Yousif Ahmadi | Add to During Fabrication: For each component: pressure test, NDE, Visual and dimensional check "R"