## 010-A-PFD-00001-005-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Refer to the first sheet for the General Comments.
2 | Call-out | 1 | Ahmed Ali | E0023
3 | Callout | 1 | Mohamed Ayyash | Add "SR" before the name
4 | Text Box | 1 | Ahmed Ali | All equipment to be updated with the new numbering
5 | Callout | 1 | Mohamed Ayyash | UNSTABILISED (Typo)
6 | Call-out | 1 | Ahmed Ali | TC 147 was above tray No.8 in the FEED PFD while it is showing in above tray No.8 here
7 | Call-out | 1 | Ahmed Ali | was not in the FEED PFD, what it purpose?
8 | Call-out | 1 | Ahmed Ali | delete
9 | Call-out | 1 | Ahmed Ali | General note: routing sheet to be mentioned
10 | Text Box | 1 | alexis.martinez | GENERAL: Equipment TAG number shall be modified based on the list and PFDs Mark-up sent to Contractor.
11 | Text Box | 1 | alexis.martinez | GENERAL: All the utility stream and the correspondent Heat and Material Balance stream number shall be shown on a separate Utility Flow Diagram (UFD).
12 | Cloud+ | 1 | 986131 | SIMPLIFY THE SECTION BY REARRANGING THE PUMP LOCATION TO MINIMISE LINE CROSSINGS. AVOID BREAKING THE MAIN FEED LINE.
13 | Cloud+ | 1 | 986131 | SIMPLIFY THE SECTION BY REARRANGING THE PUMP LOCATION TO MINIMISE LINE CROSSINGS. AVOID BREAKING THE MAIN FEED LINE.
14 | Cloud+ | 1 | 986131 | SIMPLIFY THE SECTION BY REARRANGING THE EXCHANGER LOCATION TO MINIMISE LINE CROSSINGS. AVOID BREAKING THE MAIN FEED LINE.
15 | Text Box | 1 | alexis.martinez | GENERAL COMMENT APPLICABLE TO ALL PFD'S: - As required in BMPS A8, 7.2.7 item 4 add the note stating: The data on equipment data blocks indicate the normal operating case for the unit and may not be the design case. - All tag numbers shown close to or inside the equipment to have the full equipment number including the unit number - this is based on the updated BMPS-A8 (issued on 09 April 2018)
16 | Callout | 1 | alexis.martinez | Add stream number for stream from sour water sump pump and include this in the heat and material balance
17 | Text Box | 1 | alexis.martinez | GENERAL: locate the equipment data blocks aligned with the corresponding equipment.
18 | Call-out | 1 | alexis.martinez | Replace "TO FLARE OR FUEL GAS SYSTEM" to "TO FLARE" in the vent from stabilizer reflux drum.
19 | Call-out | 1 | alexis.martinez | Design pressure of naphtha splitter reflux drum is not matching with FEED data sheet.