## 010-G-DAT-00001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mahdi Ali | Remove space.
2 | Text Box | 1 | Hasan Asad | The below points are applicable to all data sheets attached within this transmittal: 1. Instrument for bearing pump/bearing vibration and bearing temperature shall be as per Machinery Monitoring Instrument Table (doc. No. 2520-z000-NM-1515-03-A) and JV rotating equipment criticality assessment. 2.Mechanical seal selection shall be in accordance to Seal OEM selection chart and High Consequence Pump criteria as specified in BMPS G9 shall be considered as well. 3.Bearing life shall be calculated and provided. 4.Complete unit test requirement shall be selected case by case. 5.Owner standardized on John Crane mechanical seal with a long term contract for reliability services, seal repair and test and supply of inventory. Owner preference is John Crane due to standardization and seal spare interchangeability. 6.The seal API plan shall be accessible and a filling cart is provided for filling the seal pot. 7.Close clearance metallized throat bushing for optimal control of stuffing box pressure (Pump Vendor to advice). This is important to secure seal stuffing box pressure. 8.Labyrinth bearing housing isolators suitable for oil mist system.
3 | Callout | 1 | Isamu | Delete
4 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all document
5 | Text Box | 1 | Sameer Foujdar | As a general comment cooling water inlet and return pressure to be verified for all the pumps as per BMPS A1 for all the pumps 010P 0001/2/29/7/10/19/12 A/B.
6 | Call-out | 2 | 986131 | Completed the missing information for max, nor and min case
7 | Callout | 2 | alexis.martinez | GENERAL: For decimal separator use dot (.) instead of coma (,)
8 | Call-out | 2 | Tapas | For process data in Row 20 to 25: Provide the detailed engineering work carried out to arrive at the numbers.
9 | Call-out | 2 | Tapas | Add chlorides
10 | Cloud+ | 2 | Adnan Alothman | Pressure parameters in the Operating Conditions table need to be checked (against FEED DS) and confirmed
11 | Call-out | 2 | Tapas | Chloride in Cooling water is expected to be higher based on chemical addition - applies to all pumps using Cooling water.
12 | Cloud+ | 2 | Yousif Ahmadi | Per FEED document the normal Vapor pressure is 4. Verify and confirm.
13 | Callout | 2 | Mohamed Ayyash | Overlapping (Correct)
14 | Callout | 2 | Mohamed Ayyash | Add 7CDU (in all pages)
15 | Callout | 3 | Mohamed Ayyash | Correct, overlap
16 | Callout | 4 | Mohamed Ayyash | Align
17 | Callout | 4 | Adnan Alothman | Seal supp. sys. mounted on Pump Baseplate to be checked and confirm against relative standard.
18 | Call-out | 6 | Jawad Alawi | Typical: Specify the refered to Standard
19 | Text Box | 6 | Ahmed Marhoon | The following are general comments related to instrumentation and control: 1. The notes related to Instrumentation & Control provided on the Data Sheet do not capture all the technical requirements for the instruments design. All applicable BMPS-J series to be referenced (such as J2, J3 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Minimum Flow arrangement/design shall be reviewed and confirmed by the supplier. 6. Supplier to be notified on consideration of the Permissive (linked to MOVs status) requirements per the PID. 7. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 8. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 9. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 10. All the machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 11. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 12. Assistance and involvement of the vendor during CHAZOP/Hazop workshops and study to be considered. 13. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 14. Scope of supply for the interposing relays to be clearly defined. 15. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 16. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31.
20 | Callout | 7 | Mohamed Ayyash | space
21 | Call-out | 7 | Mahdi Ali | Motor equipment code is 'M' and not 'PM'
22 | Text Box | 7 | Sankara | Delete Ex p
23 | Callout | 7 | Mohamed Ayyash | Delete P
24 | Callout | 7 | Mohamed Ayyash | Make space move the box
25 | Callout | 7 | Mohamed Ayyash | deg F is Hidden ?
26 | Cloud | 7 | Mohamed Ayyash
27 | Callout | 7 | Mohamed Ayyash | This is a Motor
28 | Callout | 7 | Mohamed Ayyash | This is crude feed pumps data sheet
29 | Callout | 8 | Mohamed Ayyash | Align
30 | Call-out | 8 | Tapas | provide unique note numbers in this Data sheet. refer page 9. [This comment applies to all the data sheet in this transmittal]
31 | Call-out | 9 | Mahdi Ali | Always quote Bapco number
32 | Callout | 9 | Isamu | Please make clear as this wordings make confusion during pump selection by Vendor