## 010-G-DAT-00002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mohamed Ayyash | No. (Typo) apply to all document
2 | Call-out | 1 | Mahdi Ali | Remove space in the Tag number
3 | Callout | 1 | Isamu | Delete
4 | Callout | 1 | Mohamed Ayyash | Delete
5 | Call-out | 2 | Tapas | Add chlorides
6 | Call-out | 2 | Tapas | Completed the missing information for max, nor and min case
7 | Callout | 2 | alexis.martinez | GENERAL: For decimal separator use dot (.) instead of coma (,)
8 | Callout | 2 | Mohamed Ayyash | Add 7CDU (in all pages)
9 | Call-out | 2 | Tapas | For process data in Row 21 to 26: Provide the detailed engineering work carried out to arrive at the numbers.
10 | Call-out | 2 | Tapas | Add Caustic 2 PTB future case.
11 | Callout | 3 | Mohamed Ayyash | Correct, overlap
12 | Callout | 4 | Mohamed Ayyash | Align
13 | Callout | 4 | Yousif Ahmadi | Add COOLING WATER PIPING MATERIALS: CS
14 | Callout | 4 | Adnan Alothman | Seal supp. sys. mounted on Pump Baseplate to be checked and confirm against relative standard.
15 | Text Box | 6 | Ahmed Marhoon | The following are general comments related to instrumentation and control: 1. The notes related to Instrumentation & Control provided on the Data Sheet do not capture all the technical requirements for the instruments design. All applicable BMPS-J series to be referenced (such as J2, J3 …etc) for the supplier to comply with. 2. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification that will be sent out to suppliers. In case this document would be the only one for MR, then all the relevant BMPS to be included in the Data Sheet notes. 3. Vendors to be notified on the fact that the final design of the system shall include all the Hazop3/SIL recommendations and approved PID post-EPC-development. 4. Since the Data Sheet is issued separately, the consistency between the different documents, that may be part of the requisition, could not be verified and hence it is the contractor’s responsibility to update the other documents impacted by any of the comments on this Data Sheet and vice versa. 5. Minimum Flow arrangement/design shall be reviewed and confirmed by the supplier. 6. According to Note 6 on sheet 8 of BRA-227060 (FEED revision) PID, EPC contractor to verify the requirement of low suction pressure trip of pumps. The protections required for the equipment shall be carefully reviewed and addressed with the supplier. 7. Add Design Philosophy BMPS-A3 reference section 8.5 MCM Guidelines. Monitoring system in general to meet the requirement stated in this BMPS in addition to vendor requirement. 8. Requirement of MCM to be verified with the supplier. Reference to BMPS-J15 MCM to be added accordingly. 9. Suppliers to be notified on the possibility of considering wireless instruments for non-critical monitoring devices. Reference to BMPS-J10 Wireless to be added if applicable and meeting the criteria (under development) of wireless measurement. 10. All the machinery monitoring probes etc. shall be factory fitted by the vendor and not at site. 11. Narrative/flow charts/cause and effect shall be provided for any control or sequence logic. 12. Assistance and involvement of the vendor during CHAZOP/Hazop workshops and study to be considered. 13. Explanatory notes to be added on the requirement of having the control performed in the plant DCS and safety functions in ESD system. 14. Scope of supply for the interposing relays to be clearly defined. 15. In addition to BMPS J Specifications, all relevant BMPS J Standard/Typical Drawings to be included. 16. Add a note to the supplier to design, fabricate and supply the instruments in accordance with the BMPS J specifications. Items such as Junction boxes, cables, wiring, ferruling, earthing, terminal strips, fitting …etc shall be installed by the vendor/contractor meeting the requirements specified on the applicable BMPS J specifications like BMPS-J31.
16 | Callout | 7 | Mohamed Ayyash | This is a Motor
17 | Callout | 7 | Mohamed Ayyash | Delete P
18 | Call-out | 7 | Mahdi Ali | Motor equipment code is 'M' and not 'PM'
19 | Callout | 8 | Mohamed Ayyash | Align
20 | Call-out | 9 | Mahdi Ali | Always quote Bapco number
21 | Callout | 9 | Isamu | Please make clear as this wordings make confusion during pump selection by Vendor
22 | Callout | 9 | Mohamed Ayyash | -32.8 ( replace comma with dot)
23 | Callout | 9 | Mohamed Ayyash | pour point (Typo)
24 | Text Box | 9 | Ahmed Ali | Add the following note: in future there will be caustic injection facility at the outlet of the desalter (upstream of the desalted feed pumps, all equipment downstream to be designed for x ppm of caustic