## 011-C-GAD-10001-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 4 | 986131 | - As per P&ID a tangential inlet distributor is to be used. Please correct. - Nozzle N1 is not a tangential entry please correct.
2 | Call-out | 1 | MAK | 1
3 | Call-out | 2 | MAK | 1
4 | Call-out | 3 | MAK | 1
5 | Call-out | 4 | MAK | 1
6 | Call-out | 2 | MAK | 2
7 | Call-out | 3 | MAK | 3
8 | Text Box | 1 | MAK | 4
9 | Call-out | 4 | MAK | 4
10 | Text Box | 1 | MAK | 011 - 7VDU
11 | Text Box | 2 | MAK | 011 - 7VDU
12 | Text Box | 3 | MAK | 011 - 7VDU
13 | Text Box | 4 | MAK | 011 - 7VDU
14 | Cloud+ | 1 | Adnan Alothman | Add negative "-" to the Ext. Design Pressure values.
15 | Text Box | 4 | 986131 | Applicable for all the details shown on this drawing: Mark the details on the GA Drawing.
16 | Callout | 1 | Adnan Alothman | As per FEED drawing, N4 is 6 inch. Check and confirm
17 | Callout | 1 | Yousif Ahmadi | Change to SA 194 2H
18 | Call-out | 4 | 986131 | From the drawing area of the slotted section is not clear. provide more details/ explanation.
19 | Cloud+ | 3 | 986131 | Gravity distributors to be used.
20 | Cloud+ | 3 | 986131 | Gravity distributors to be used.
21 | Callout | 1 | alexis.martinez | In page 1, Nozzle table, shows the nozzle size N1 in inch.
22 | Callout | 1 | alexis.martinez | In page 1, Nozzle table, use the hyphen symbol (  ) instead of division symbol ( ÷ ) on nozzle N28A-C and M3-5
23 | Callout | 2 | alexis.martinez | In Page 2, Note 21, add the column pressure drop and the liquid static head used to calculate the design pressure at Bottom Tangent Line (B.T.L.)
24 | Text Box | 1 | Ahmed Ali | new nozzle for MVGO recycle to be added as per bapco new load calculation
25 | Callout | 1 | alexis.martinez | Page 1, Nozzle Table: As per page one on document 010-C-GAD-10001-001-RAP (Atmospheric Column 010C0001), add "A/B" to Nozzle N17, i.e. to be shown as N17A/B.
26 | Callout | 1 | alexis.martinez | Page 1, Nozzle Table: Replace on nozzle row N8 by VACUUM RESIDUE" the word "LIQUID"
27 | Callout | 3 | alexis.martinez | Page 3, The Manhole M8 to be located above the elevation of N6 and for M4 above the elevation of nozzle N4
28 | Callout | 3 | alexis.martinez | Page 3, The nozzle N18A shall be above the Nozzles N17A/B and N19A to cover the entire liquid level.
29 | Cloud+ | 3 | 986131 | Please ensure the quench provided is properly mixed with the bottom liquid and show the details of the distributor.
30 | Cloud+ | 3 | 986131 | provide distribution arrangement for the nozzle and show the details in next page
31 | Cloud+ | 3 | 986131 | Provide the details of the section in the next page. The current arrange shown is inadequate to ensure proper liquid distribution to the stripping section.
32 | Cloud+ | 1 | 986131 | Repeat this on all page - drawing name and equipment number must be added on all pages of the document.
33 | Call-out | 4 | 986131 | Show support details on the drawing.
34 | Cloud+ | 3 | 986131 | The arrangement currently shown is inadequate for proper liquid distribution to the stripping section. This need to be correctly shown. the details to be shown in the next page.
35 | Text Box | 1 | MAK | Use the latest A3 Border
36 | Text Box | 2 | MAK | Use the latest A3 Border
37 | Text Box | 3 | MAK | Use the latest A3 Border
38 | Text Box | 4 | MAK | Use the latest A3 Border