## 011-C-GAD-10002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Unlocked | 2
2 | Call-out | 2 | Unlocked | 2
3 | Call-out | 3 | Unlocked | 2
4 | Call-out | 2 | Unlocked | 2
5 | Text Box | 1 | Unlocked | 3
6 | Call-out | 3 | Unlocked | 3
7 | Text Box | 1 | Unlocked | 011 - 7VDU
8 | Text Box | 2 | Unlocked | 011 - 7VDU
9 | Text Box | 3 | Unlocked | 011 - 7VDU
10 | Cloud+ | 1 | Unlocked | Add negative "-" to the Ext. Design Pressure values.
11 | Cloud+ | 1 | Unlocked | As per FEED Drawing the values of 1st Design Temp. are 165. Check and confirm
12 | Callout | 1 | Unlocked | Change to SA 194 2H
13 | Callout | 1 | Unlocked | Fire Proofing is required per FEED drawing. Check and confirm.
14 | Call-out | 3 | Unlocked | No oil skimming arrangement is shown. Please review the requirement of oil skimming.
15 | Cloud+ | 3 | Unlocked | Nozzle N2 to be connected to a distribution device for uniform liquid low to the packed bed. Details to be provided.
16 | Cloud+ | 3 | Unlocked | Show details of the arrangement.
17 | Cloud+ | 1 | Unlocked | Title per FEED document is AMINE ABSORBER.
18 | Text Box | 1 | Unlocked | Use the latest A3 Border
19 | Text Box | 2 | Unlocked | Use the latest A3 Border
20 | Text Box | 3 | Unlocked | Use the latest A3 Border