## 012-A-EQL-00001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 3 | 986131 | Rename as - STABILIZER FEED/ BOTTOM EXCHANGER Applies to UNIT 17 also.
2 | Call-out | 4 | 986131 | Note the compressor & associated equipments to be retained in the list ADD: 012K0001A and 012K0001B and the details Applies to unit 17 also.
3 | Cloud+ | 6 | 986131 | Rename as STEAM CONDENSER AIR COOLER FINFAN Also applies to unit 17.
4 | Cloud+ | 8 | 986131 | Rename as STEAM CONDENSER AIR COOLER ELECTRIC MOTOR Also applies to unit 17.
5 | Call-out | 10 | 986131 | Note the compressor & associated equipments to be retained in the list ADD: 012V0001 and the details Applies to unit 17 also.
6 | Cloud+ | 10 | 986131 | Consider naming as STABILIZER SILENCERS Also applies to UNIT 17
7 | Cloud+ | 10 | 986131 | Consider naming as NAPHTHA SPLITTER SILENCERS Also applies to UNIT 17
8 | Text Box | 1 | MAK | General Comment: Use the latest document template issued to TTSJV as part of the Homogenization Procedure. The cover page shall be orientated the same as the documents they apply to.
9 | Text Box | 1 | MAK | FEED GAS COMPRESSORS 012K0001A/B and FEED GAS COMPRESSOR ELECTRIC MOTORS 012M0057A/B missing from the list. Why?
10 | Text Box | 1 | MAK | FEED GAS COMPRESSOR K.O. DRUM 012V0001 missing from the list. Why?
11 | Text Box | 1 | MAK | General Comment: Change the word NAPTHA TO NAPHTHA in the entire list.
12 | Call-out | 4 | MAK | Correct to AIR COOLER
13 | Call-out | 4 | MAK | Correct to NAPHTHA
14 | Call-out | 6 | MAK | Correct to AIR COOLER
15 | Call-out | 8 | MAK | Correct to AIR COOLER
16 | Call-out | 10 | MAK | Change to 012OMG0001
17 | Call-out | 10 | MAK | Change to 012U0003
18 | Call-out | 10 | MAK | Change to 012U0002
19 | Call-out | 1 | Raj | The Item Index has mainly been reviewed for the Equipment Numbering. Many design parameters cannot be checked as preceding engineering documents such as equipment datasheets, MSD etc has not been submitted/completed
20 | Text Box | 1 | Yousif Ahmadi | General comments for all Equipment index - Use the new template - Provide Technip Group Spec. 000 GOPS 2014. - Fill the missing cells with the available information. - For new equipment in Existing units use the numbers as were agreed with Bapco.