## 018-A-PFD-00001-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud |  | Hasan Asad
2 | Cloud |  | Hasan Asad
3 | Text Box |  | Hasan Asad | Correct basis new equipment list to match.
4 | Text Box |  | Hasan Asad | Correct basis new equipment list to match.
5 | Cloud |  | Hasan Asad
6 | Text Box |  | Hasan Asad | Correct to: K0001
7 | Text Box |  | Hasan Asad | General comment: All equipment tags shall be in accordance to equipment tag. K1001 shall be 18K1001.
8 | Call-out |  | Ravi Kumar | Delete "SECTIOPN" - repeated
9 | Highlight |  | Fatema Hashem
10 | Callout |  | Fatema Hashem | CORRECT THE PRESSURE OF LINE 165B TO 694 PSIG
11 | Cloud |  | Fatema Hashem
12 | Callout |  | Fatema Hashem | FLARE LINE TO BE TERTIARY THICKNESS
13 | Callout |  | Fatema Hashem | CORRECT LINE 260 DESCRIPTION" HYDROGEN TO TR2 MAKE-UP COMPRESSOR 1ST STG SUCTION DRUM V2010"
14 | Highlight |  | Fatema Hashem
15 | Highlight |  | Fatema Hashem
16 | Callout |  | Fatema Hashem | CORRECT LINE 159 DESCRIPTION" HYDROGEN FROM 3/4 H2P"
17 | Highlight |  | Fatema Hashem
18 | Callout |  | Fatema Hashem | MODIFY DESCRIPTION: "HYDROGEN FROM TR2 FIRST STAGE SUCTION DRUM V2010"
19 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: FIRST STAGE
20 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: FIRST STAGE
21 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: FIRST STAGE
22 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: SECOND STAGE
23 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: SECOND STAGE
24 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: SECOND STAGE
25 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: THIRD STAGE
26 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: THIRD STAGE
27 | Text Box |  | Fatema Hashem | ADD DESCRIPTION: THIRD STAGE
28 | Callout |  | Fatema Hashem | SHOW PRESSURE AND TEMPERATURE LEGEND ON THIS PFD TOO FOR LINE 139.
29 | Cloud |  | Fatema Hashem
30 | Callout |  | Fatema Hashem | CORRECT LINE THICKNESS TO SECONDARY
31 | Callout |  | Fatema Hashem | COMPLETE THE PC TAG NUMBER IN THE SIGNAL DESCRIPTION. "FROM PC 1023 ON V1002"
32 | Highlight |  | Fatema Hashem
33 | Cloud |  | Fatema Hashem
34 | Callout |  | Fatema Hashem | CORRECT LINE THICKNESS TO SECONDARY
35 | Cloud |  | Fatema Hashem
36 | Callout |  | Fatema Hashem | MOVE VESSEL DETAILS TO BE VERTICALLY ALIGNED WITH THE VESSEL POSITION ON THE DRAWING. GENERAL COMMENT.
37 | Callout |  | Fatema Hashem | MODIFY V1010 DESCRIPTION TO "TR1 MAKE-UP COMPRESSOR FIRST STAGE SUCTION DRUM" FOR CLARITY
38 | Highlight |  | Fatema Hashem
39 | Callout |  | Fatema Hashem | CORRECT DESCRIPTION TO: "HYDROGEN TO TR2 MAKE-UP COMPRESSOR DISCHARGE HEADER"
40 | Highlight |  | Fatema Hashem
41 | Highlight |  | Fatema Hashem
42 | Callout |  | Fatema Hashem | CORRECT DESCRIPTION TO: "HYDROGEN FROM TR2 MAKE-UP COMPRESSOR SECOND STG COMMON DISCHARGE HEADER"
43 | Callout |  | Fatema Hashem | CORRECT DESCRIPTION TO: "HYDROGEN FROM TR2 MAKE-UP COMPRESSOR SECOND STG COMMON DISCHARGE HEADER"
44 | Highlight |  | Fatema Hashem
45 | Highlight |  | Fatema Hashem
46 | Highlight |  | Fatema Hashem
47 | Highlight |  | Fatema Hashem