## BAPCO DOC. CODE-REV-CS
ID N° | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | A.Jabbar Mahmood | Typo in the title: NAPHTHA SPLITTER | Noted. It will be implemented in revision A | Y
2 | Callout |  | A.Jabbar Mahmood | External design pressures shall be reported as negative values (vacuum) i.e. as -10 psig | It is indicated external pressure. Hence, it is not necessary to include additionally -10 PSIG | N
3 | Text Box |  | A.Jabbar Mahmood | A note should be added indicating that the sizes of the column nozzles may change during the development of the detailed design. | Not all nozzle sizes are on hold and shall be fixed in order to have Vendor quotation. In any case, this is the reason why Contractor included optional prices for nozzles in RFI. | N
4 | Callout |  | alexis.martinez | The equipment TAG number and the description shall be shown in all the sheets. | TTSJV is checking Owner comments to all Material Requisitions and the templates will be revised accordingly to be implemented in the OC deliverables.
5 | Cloud+ |  | Ahmed Marhoon | The current revision indicates the instrumention connections based on the current PID revision. Vendor shall be notified on the possibility of having more connections (especially for the level instruments) after design development and post-Hazop3. E.g. if a trip command is envisaged per Hazop/SIL studies, then new tappings will need to be provided for the ESD LITs to meet the specifications. This is typical comment for all equipment data sheets across BMP units. | Noted. It will be implemented in revision A | Y
6 | Call-out |  | Ahmed Marhoon | Add Unit Name according to the WBS: for this case (2HCU) | Noted. It will be implemented in revision A | Y
7 | Callout |  | A.Jabbar Mahmood | TYPO in Note 22: drop | Noted. It will be implemented in revision A | Y
8 | Callout |  | A.Jabbar Mahmood | Use "dot" for decimal point. | Noted. It will be implemented in revision A | Y
9 | Cloud+ |  | Ahmed Marhoon | Based to the PID, EDP's GAD and to avoid dead-legs in the level bridle, lower level tapping (45B) needs to be relocated to the side of the column. The new tapping elevation shall still cover the LLL of the operating range. | This is a preliminar sketch. This nozzle will be relocated by instrumentation department in a later stage | N
10 | Cloud+ |  | Ahmed Marhoon | Direction to North, is it applicable for this drawing? If applicable, is it shown at the right direction? Otherwise, delete from the drawing. Typical for similar drawing. | Orientations are on hold. However north indicates always 0º | N