## 019-E-DAT-00003-001
ID Nº | Subject | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Stamp | Raj
2 | Cloud+ | A.Jabbar Mahmood | Report the H2S in the liquid phase in mass basis as ppm wt | MOC Process: 'wt' will be added to the reported values. | To be updated
3 | Cloud+ | A.Jabbar Mahmood | Note 19: Should both be based on the same design case (EOR)? | MOC Process: Note 19 will be updated 'Shellside: Minimum flowrate with unit at turndown operation (case operating EOR): 49.6% of Design Case EOR. | To be updated
4 | Cloud+ | A.Jabbar Mahmood | Note 20: The reported composition is for the Design Case SOR. Revise the data based on Design Case EOR. | MOC Process: Noted, composition will be updated based on Design Case EOR. | To be updated
5 | Text Box | A.Jabbar Mahmood | Consider adding note 11 of the licensor's datasheet for information | Updated by D/S Note (31) "11. TUBE SUPPORT PLATES ARE CROPPED ON TOP AND BOTTOM FOR DRAINAGE PURPOSES ONLY." | Y