## 019-S-DAT-00005-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Page 1 | A.Jabbar Mahmood | This cannot be called a "mechanical" datasheet. This appears to be a 'specification' sheet for the filter package.
2 | Text Box | Page 1 | Ahmed Marhoon | The notes related to Instrumentation & Control provided on the last sheet are general in nature. TTSJV is requested to ensure that all the specific technical/functional requirements (including AVL) are covered and detailed in the requisition specification (not yet issued) that will be sent out to suppliers. For example, note 15 on page 3, briefly describe the scope of the package supplier for the instrumentation with no reference to the relevant BMPS-J class or PID and so on. Also, vendors to be notified on the fact that the final design of the system shall include all the Hazop/SIL (where the vendor will be involved) recommendation and approved PID. Since the Data Sheet is issued separately, the consistency between the different documents, that will be part of the requisition, could not be verified and hence it is the contractor's responsibility to update the other documents impacted by any of the comments on this transmittal and vice versa.
3 | Stamp | Page 1 | mark.langerhorst
4 | Cloud+ | Page 2 | A.Jabbar Mahmood | The design pressure may need to be revised based on the shutoff pressure of selected upstream pump. A note shall be added in this regards.
5 | Cloud+ | Page 2 | A.Jabbar Mahmood | A note shall be added indicating that the mechanical design temp will be upgraded to 500F as the filters are classified as vessels.
6 | Cloud+ | Page 2 | Yousif | What will be the joint Efficiency
7 | Call-out | Page 3 | Hasan Al Noaimi | bank
8 | Text Box | Page 3 | A.Jabbar Mahmood | Note 1 of the FEED datasheet shall be retained
9 | Cloud+ | Page 3 | A.Jabbar Mahmood | The pressure as per the FEED D/S and PFD is 124 psig (inlet). Owner's understanding is that the outlet pressure if set by the Feed Surge drum pressure 70 psig and the inlet by the pressure drop across the filter. TR to check and confirm.
10 | Callout | Page 3 | Mohamed Ayyash | be (spilling)
11 | Call-out | Page 3 | Ali Abbas | P&IDs,
12 | Call-out | Page 3 | Ali Abbas | (including flow chart)
13 | Call-out | Page 3 | Ahmed Marhoon | To avoid future misunderstandings and to be in line with PID; replace "PDT" with "PDIT"
14 | Text Box | Page 3 | Hasan Asad | Maintenance strategy during T&I shall be provided together with spare part list and troubleshooting guideline.