## 021-K-DAT-00002-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Ali Kadhem | 1. Values for RATED, NORMAL and MINIMUM for INLET and EXHAUST are not matching with BMPS-A1. Please check and revise. 2. As per note no.5 of the datasheet, 10 psi pressure drop between header and turbine was considered for some cases only. Please provide rational for this and ensure consistency for all the cases.
2 | Text Box | 5 | Hasan Asad | As per BMPS-A3, 3 axial probes shall be provided.
3 | Call-out | 7 | Rashed Almudahka | Start-up assistance and vendor witness initial alignment are required as per FEED document. please clarify
4 | Call-out | 7 | Rashed Almudahka | Coupling ring and plug gauge is required as per FEED document. please clarify