## 023-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
SWJMDCPBYAESPYQL | Note | Page 1 | Julio.Aguilar | Ranjit, Mark: I understand that the coolers E0006A/B (NNF process side) will be used during startup or any emergency with the coolers in duty (E0005A/B). However the CW all the time will be aligned. Thus, the water consumption for this cooler is to be considered in the circulation water balance for the CLCW system.
POZRGAECUFWDAJEP | Callout | Page 1 | A.Jabbar Mahmood | The operating pressure of both 3HDU and 2HCU CLPS vapours are shown as 445 psig in the H&MB data table. Hence, either the pressure of the combined stream is reduced to 445 psig or the battery limit pressures are adjusted taking into account the battery limit pressures at the source units.
DVWFLEYJMLDKYUFN | Call-out | Page 1 | Ali Hasan | The sheet no. shall be shown within the document no. Follow BMBS-A8. This is a general comment.
RMUFGHMFMIPWZOHC | Call-out | Page 1 | Ali Hasan | show valve in closed position
BOCIJWUDFVGJZSVL | Call-out | Page 1 | Ali Hasan | Delete the # sign
COARVXMRQNFDMBEN | Call-out | Page 1 | Ali Hasan | show valve in closed position
GUNUIRNAVPOJHOKO | Callout | Page 1 | Mohamed Ayyash | Manual valves are usually shown on closed position not C/Vs
DZMOFJHQNDLJNDYI | Arrow | Page 1 | Mohamed Ayyash
NAHCYRAZNGIYYJHJ | Call-out | Page 1 | Ali Hasan | show as block valve, keep it in closed position
HDNBCNWJQEUXOGLE | Call-out | Page 1 | Ali Hasan | show as block valve, keep it in closed position
RFPQERZUCBBGUVIW | Line | Page 1 | Ali Hasan
EEYBLPRPBQCWBDPD | Cloud | Page 1 | Ali Hasan
QLTWWNRAXWBMAHTI | Cloud | Page 1 | Ali Hasan
PFNZLNUEDKRQNEEQ | Line | Page 1 | Ali Hasan
RXDLOSXRQDUWOBEY | Line | Page 1 | Ali Hasan
YRZVGCHIPJJGAKTE | Line | Page 1 | Ali Hasan
IRUPAXOTJVKJTEJY | Line | Page 1 | Ali Hasan
GUPNSMZOKSPUDXHN | Call-out | Page 1 | Ali Hasan | In accordance to the FEED documentation and design, the Amine absorber bypass shall only bypass the Amine column, and not the PSA inlet cooler and the Amine absorber KO drum. The FEED design shall be retained and hence, the bypass arrangement in the PFD shall be revised. In case of high-high level in the Amine absorber KO drum, the PSA will shutdown by ESD action. If the KO drum is included in the bypass arrangement, then this trip interlock will not be available.
RJGTIGXMUPTMXWCH | Arrow | Page 1 | Ali Hasan
QSUYPADDLSLIZZIO | Call-out | Page 1 | Ali Kadhem | 111 F as per H&MB. Please confirm/revise.
HGPBISWQYPNQVZIR | Cloud | Page 1 | Ali Hasan
MBRCYPZKSBVZVNWG | Cloud | Page 1 | Ali Hasan
FMOQRUHEGKCIIFXT | Arrow | Page 1 | Ali Hasan
RAFJPEHRKKUITKIP | Call-out | Page 1 | Ali Hasan | 1.Change 2HDU off-gas description to Unifiner Separator (V18) off-gas 2.The Unifiner stream shall be connected to 2HDU LPS off-gas, as specified by Owner in T1967. Show the Unifiner stream connected to 2HDU stream in the PFD. 3.Show Unifiner stream as NNF with block valve in closed position. Add the following note for the Unifiner stream instead of Note 6: A provision is made to route Unifiner V18 offgas to 2HDU LPS offgas in future and route to 1HRU as feed. However Unifiner V18 off-gas stream is not included in 1HRU H&MB. Before routing V18 offgas to 1HRU, a detailed assessment of the impact of processing this stream shall be made as per Management of Change procedure.
HJVUFXZLMSQOKNON | Call-out | Page 1 | Ali Hasan | Add TI0006
XLLGJHDLJSZMDVET | Call-out | Page 1 | Ali Hasan | Add TI0007
TYYJOTGTTIRWCBKY | Call-out | Page 1 | Ali Hasan | Add TI0002
ZWCSGDXLZXNTMPFP | Call-out | Page 1 | Ali Hasan | Add TI0023A
YVSIZOASCEDXTCKR | Call-out | Page 1 | Ali Hasan | Add TI0136
BIFFHQMFOBHZEPAI | Cloud | Page 1 | Ali Abbas
UPIYUSMVDFYHTTMU | Call-out | Page 1 | Ali Abbas | Delete as PTs,FTs &TTs are connected directely to ASC
HLWAJGDFQLFXHGUV | Call-out | Page 1 | Ali Abbas | Refer to BMPS-J16 Anti-Surge Control System for No. of FTs,PTs and TTs requirements.
LGKFWTATQCSDMJUL | Call-out | Page 1 | Ali Abbas | These numbers outside the instrument circle are not clear. A note to be added for clarity and tag nos to be in sequence.
VNVLBKFRYEVVUQBT | Call-out | Page 1 | Ali Abbas
ZIZFVMGRIGZLXSDT | Call-out | Page 1 | Ali Abbas
QNKIRPGLPPZZLDCH | Call-out | Page 1 | Ali Abbas
AJSHPXGNLIYKGGUZ | Call-out | Page 1 | Ali Abbas
FJFZIFQMOXTWIKTH | Call-out | Page 1 | Ali Kadhem | Add FI0021
AKRUYDXAIIOVXAYU | Call-out | Page 1 | Ali Kadhem | Add FI0047 Add TI0078
KMVQTWKYPLBYKLVP | Call-out | Page 1 | Ali Kadhem | Add reference PFD numbers
ECQAEJRBDJHJMSZO | Pen | Page 1 | Ali Kadhem
JUSXNHZWXIYZVXHQ | Arrow | Page 1 | Ali Kadhem
LFQVYATVYATYRGCV | Arrow | Page 1 | Ali Kadhem
USIFFQVCNREYMLNO | Call-out | Page 1 | Ali Kadhem | 1.As per H&MB, the pressure of streams 1A, 1B and 1C are 445psig, 445psig and 450psig, respectively. The pressure of the combined stream as per H&MB i.e. stream no.1 is 445psig. Please ensure consistency. 2.As a general comment, please ensure that the B/L pressures are consistent. These pressures should be consistent with upstream and downstream units, and should also account for pressure drop in the interconnecting piping.
VPEOBUHNEVLOVDZD | Arrow | Page 1 | Ali Kadhem
SAXCIAMJDWPHOCOV | Arrow | Page 1 | Ali Kadhem
FRIZIFBZCLWTEZRN | Arrow | Page 1 | Ali Kadhem
KPTFLCCENGSUCHJB | Call-out | Page 1 | Ali Kadhem | Currently this stream joins the 3HDU sour gas to 1 & 2 SGP line inside 3HDU battery limit as per the P&ID BRA-226873 Sheet 1. A comment was provided in the 3HDU PFD to show this line and update the H&MB for 3HDU PFD. Therefore, the reference PFD number and description to be updated as well in 1HRU PFD (show this line going to 3HDU PFD)
VKBEAWPDZWEQMDAT | Text Box | Page 1 | Ravi Kumar | TTSJV to check and confirm that Bid Queries/Responses to T1003, T1004, T1005 are addressed and included in the PFDs
QNGEDLDBTZHSXNJM | Arrow | Page 1 | Ali Hasan
MSWGNBOXYVXONHLX | Line | Page 1 | Ali Hasan
BODNNEXLJTOYRBBR | Line | Page 1 | Ali Hasan
RSATHICIYAOMFMGL | Call-out | Page 1 | Ranjit | DELETE THIS LINE. COLUMN BYPASS LINE SHOULD PASS THROUGH E0004 AS SHOWN
QSBUNUBHWDWZDHJT | Stamp | Page 1 | Ranjit