## 036-E-DAT-00001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
2 | Callout | Page 1 | Salman Jaffer | Insert unit name | Will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | N
3 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs | All have been implemented, but will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | Y
4 | Text Box | Page 1 | Dowon Pyun | Typical comments to all; 1. Contractor shall recheck the philosophy of process temperature control per each item considering the minimum requirement of para. 7.8 in BMPS-A3 and reference project P&IDs. Except for air coolers controlled by VSD, Contractor to confirm which of auto variable fan pitch and louvers are required for temperature control. 2. For the items under wet H2S service and not applied for HIC material, Contractor is required to confirm H2S dissolved partial pressure and the requirement of NACE MR0103. 3. No exchangers have applied for tube to tubesheet joint with seal or strength welds. Contractor to confirm his basis whether this requirement is applicable or not for sour services, hydrogen service, high temperature and high pressure services. 4. Line connection sizes shall be verified by mechanical in connection with fluid velocities in tubes and header boxes. | 1. BMPS-A3 para.7.8 is already reviewed and reflected. 2. Will be incorporated. 3. Confirmed. It was verified by Bid Clarification T1866. 4. Will be designed and reviewed during inquiry and reflected to PO requisition. | N
5 | Cloud | Page 2 | Mahdi Ali
6 | Callout | Page 2 | Salman Jaffer | Specify the thickness | 'Stock Thickness' cannot be specified at the inquiry stage. | N
7 | Cloud+ | Page 2 | Saeed Taher | Refer to T1568 for tubes material | Comment incorporated. The material changed to SA179. | Y
8 | Cloud+ | Page 2 | Sameer.Ahmed | This length is not as per BMPS-A1 8.2.3 | As per BMPS-A1 and BMPS-E7, preferred tube length is 16, 30, 42 ft. However, this limitation can be discussed during the EPC stage, as per Bid Clarification T883 for the economical reasons. It can be deeply discussed after TBE. | N
9 | Callout | Page 2 | Jong.Ahn | indicate P&ID number, this comment common for all data sheet | No requirement for assigning P&ID number to datasheet. P&ID number can be checked at equipment list. (Item index) | N
10 | Callout | Page 2 | balagangadhar.k | Provide note for this section Referring to BMPS-A1 & BMPS-E7. Typical for all air cooler datasheets. | BMPS-A1 & BMPS-E7 is related for all parts of air coolers, that's why those two specifications remarked as general note. No need to call. | N
11 | Callout | Page 2 | BD Mori | Specify the estimated highest temperature at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario leading to the highest possible temperature expected at inlet to the each air cooler. Based on the highest temperature if required the vendor shall perform FEA analysis. | No upset case required for higher temperature than design condition. To be reviewed with FEED/Licensor, if required. | N
12 | Callout | Page 2 | Nalini Mohan | Replace with "FRP, Tuf-Lite or equivalent". This comment is applicable to all air fin cooler datasheets | Will be clarified with vendor and incorporated into PO Material Requisition | N
13 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
14 | Callout | Page 3 | Salman Jaffer | No need for note1 because 0370E-DAT-00001-001 is already there. | Note1 is for only clue that these items are identical, in the datasheet. It can helpful for engineering, handling and operation. | N
15 | Callout | Page 3 | Salman Jaffer | a) Please refer to Bid Query T1383 for the requirement for automatic louver b) Type 'B' manifold. c) The degree of the slop for free draining purpose as per PIDs | a) Automatic louver has been applied at datasheet for air coolers of Sulphur Block as per T1383. b) Will be clarified at TBE stage c) Will be clarified at TBE stage | N
16 | Callout | Page 3 | Syed Ahmed | 3 | Comment incorporated. | Y
17 | Text Box | Page 3 | Hasan Asad | Structure vibration or individual equipment - Limits shall be as per API or ISO. | Will be clarified with vendor and incorporated into PO Material Requisition | N
18 | Callout | Page 3 | BD Mori | Do not use acronyms: Low Severity Wet H2S Service (LSS) | Comment incorporated. | Y
19 | Callout | Page 3 | Julio.Aguilar | add: according to BMPS-A3 | Minimum design temperature has been called many BMP specifications, especially BMPS-E7. No need to specify BMP-A3. | N