## 041-A-MSD-00001-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Nalini Mohan | demister should be SS, refer FEED datasheet. Typical for all Condensers
2 | Callout | 1 | Salman Jaffer | General comment: full tag number
3 | Callout | 1 | Dowon Pyun | HSS in shell side of 041E0008 is shown in sheet 4/4 of this PFD. Contractor to recheck
4 | Text Box | 1 | Nalini Mohan | Refer to sht 1 for general comments
5 | Callout | 1 | Saeed Taher | Refer to T1099 for CA of steam jacketed pipes
6 | Callout | 1 | Saeed Taher | Refractory lined. Typical for all Condensers
7 | Text Box | 1 | balagangadhar.k | Update the process flow scheme as per latest PFD. All Equipment numbers to be updated as per latest equipment list.