## 041-E-DAT-00001-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
2 | Callout | Page 1 | Salman Jaffer | Insert unit name | Will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | N
3 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs | All have been implemented, but will be updated at PO requisition as per the Homogenization Procedure (000-A-PRO-50006-1) revision. | Y
4 | Cloud+ | Page 2 | Sameer.Ahmed | As per BMPS-A1 8.2.3, standard tube size O.D. is 25.4 mm (1") | Tube OD can be used from 1 inch to 1.5 inch, as per BMPS-E7 para. F.2.4.2 | N
5 | Callout | Page 2 | BD Mori | Specify the estimated highest temperature at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario leading to the highest possible temperature expected at inlet to the each air cooler. Based on the highest temperature if required the vendor shall perform FEA analysis. | No upset case required for higher temperature than design condition. To be reviewed with FEED/Licensor, if required. | N
6 | Text Box | Page 2 | Dowon Pyun | In/Out temperatuers are same. That means no heat exchange. Contractor to confirm this. This comment is typical to 042E4211 & 042E4311. | This air cooler is to change the steam to condensate. That's why the temperature has not been changed. | N
7 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC | Will be incorporated into PO Material Requisition, after revising the equipment numbering officially. | N
8 | Callout | Page 3 | Salman Jaffer | a) Please refer to Bid Query T1383 for the requirement for automatic louver b) Type 'B' manifold. c) The degree of the slop for free draining purpose per PIDs | a) Automatic louver has been applied at datasheet for air coolers of Sulphur Block as per T1383. b) Will be clarified at TBE stage c) Will be clarified at TBE stage | N
9 | Callout | Page 3 | Salman Jaffer | Note1 can be deleted as each condenser has a separate data sheet. | Note.1 is for only clue that these items are identical, in the datasheet. It can helpful for engineering, handling and operation. | N
10 | Callout | Page 3 | Syed Ahmed | Each header box shall have 1X1.5 inch vent and 1X2 inch drain. | Vent and drain size will be 1 inch LWN, as per BMPS-E7 para 7.1.9.19. | N
11 | Callout | Page 3 | BD Mori | Follow new unit number | Comment incorporated. | Y