## 041-F-DAT-00004-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | BD Mori | The comments in this document are also applicable to 042X4201 and 043X4301
2 | Stamp |  | Nalini Mohan
3 | Text Box |  | Nalini Mohan | Owner has reviewed and commented on the MR package submitted on Contractors request to solicit quotations from vendors at the earliest. This MR stands reviewed with Status Code 3.
4 | Text Box |  | Salman Jaffer | modify to Khuff gas Sweet Khuff Gas
5 | Arrow |  | Salman Jaffer
6 | Arrow |  | Salman Jaffer
7 | Callout |  | BD Mori | Unit to be consistent with BMPS-A1. Use single unit system
8 | Arrow |  | BD Mori
9 | Text Box |  | Salman Jaffer | Retractable Electrical Spark Igniter
10 | Callout |  | BD Mori | Note 1
11 | Callout |  | BD Mori | As per design 550# saturated steam is used for the pit vent ejector. When 550# steam is not available from SRU, review the requirement of import of 550# superheated steam for Ejector and its impact on on this process stream and the ejector data sheet.
12 | Cloud |  | Salman Jaffer
13 | Text Box |  | Salman Jaffer | Please refer to Note1 above and delete this note.
14 | Arrow |  | Salman Jaffer
15 | Callout |  | Mohamed Ayyash | move to title above ( ajust title to accumodate in one line )
16 | Arrow |  | Mohamed Ayyash
17 | Line |  | BD Mori
18 | Callout |  | BD Mori | Delete
19 | Callout |  | BD Mori | Fuel Gas composition, conditions and associated notes shall be consistent with BMPS-A1. Currently fuel gas composition in BMPS-A1 is under revision.
20 | Text Box |  | Salman Jaffer | The list of notes contains notes 1, 4, 7 and 18 only. What about other notes?
21 | Text Box |  | Salman Jaffer | Since the Sweet Khuff gas is fed from BAGRU, please review requirement of maintaining note 18.
22 | Typewritten Text |  | Mohamed Ayyash | Align
23 | Arrow |  | Mohamed Ayyash
24 | Arrow |  | Mohamed Ayyash