## 042-E-DAT-00004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | MAK | 042 - NO. 6 SULPHUR RECOVERY UNIT (6SRU)
2 | Text Box | 1 | Sang.Hwang | All comments shown on 042-E-DAT-0002-001-RA shall be applied for this item too.
3 | Call-out | 1 | MAK | Change the equipment no. across this datasheet and all the documents/drawings.
4 | Callout | 9 | Salman Jaffer | Please check if this document will be given to Vendor
5 | Text Box | 1 | balagangadhar.k | Refer to the comments provided on identical equipment in Unit 041
6 | Callout | 6 | Jong.Ahn | SOC to clarify the instrument connection size as per the section 8 in BMPS-J2, since SOC is discussing with JV further to unify them. This is general comments for all equipment datasheet.
7 | Text Box | 1 | Nalini Mohan | This data sheet is not approved because the preceding documents such as MSD has not been submitted. Therefore, Contractor is advised that the Company's comments to be sent this time have not been completed accordingly.
8 | Callout | 8 | Salman Jaffer | This note should be given different number to avoid misleading with Note 1 in next sheet.
9 | Text Box | 1 | MAK | Use the latest cover sheet which is part of the Homogenization Procedure. SOC shall coordinate with JV Directorate.