## CRS
Comment Resolution SHEET
|  |  | 042-F-DAT-80004-001 | Equipment Datasheet for Burner
BAPCO Modernization Program
No. | Rev. | Page No. | BAPCO's comment | SOC's Response | Disc. | Open/Close | Remark (Or Attachment)
1 | AP | 3 | Add sweet before Khuff Gas | To be updated. | Process | Close |  | Salman Jaffer
2 | AP | 3 | We can add (00-F-GRD-80002-001) Particular Technical Specification Doc as reference page 6 and 7 for more details. | Noted. However, Datasheet is aleady called in Material Requision. Add reference page is not required. | Project |  |  | Salman Jaffer
3 | AP | 5 | Please specify which note | To be updated. | Process | Close |  | Salman Jaffer
4 | AP | 5 | Move to title above. Adjust title to accomudate | To be updated. | Process | Close |  | Mohamed Ayyash
5 | AP | 6 | Align | To be updated. | Process | Close |  | Mohamed Ayyash