## CRS
Comment Resolution SHEET
|  |  | 043-F-DAT-00001-001 | Equipment Datasheet for Reation Furnace
BAPCO Modernization Program
No. | Rev. | Page No. | BAPCO's comment | SOC's Response | Disc. | Open/Close | Remark (Or Attachment)
1 | AP | 2 | Note 13 mentioned 100 psig | Process design pressure is 50 psig. Note 13 is for mechnical requirement. | Process | Close |  | Syed Ahmed
2 | AP | 2 | No space | Noted. Will be revised. | Stationary | Close |  | Syed Ahmed
3 | AP | 2 | Material and ASTM specifications to be specified for all components. | Noted. Will be add "ASTM". Material for each components is defined by vendor. | Stationary | Close |  | Saeed Taher
4 | AP | 3 | please specify the type like "A stainless steel" | To be specified after receiving vendor information. | Process |  |  | Syed Ahmed
5 | AP | 3 | Start up | Start-up' is not matched for this note. | Process |  |  | Syed Ahmed
6 | AP | 3 | (guard or screen) to be provided to the bottom part of the Thermal Reactor and Burner | To be checked during vendor clarification. | Process |  |  | Syed Ahmed
7 | AP | 4 | please add additional two notes : *Vendor shall specify Refractory Expansion Joint provision. *Vendor shall specify Heat up rate. | To be updated. | Process | Close |  | Syed Ahmed
8 | AP | 4 | Note | To be updated. | Process | Close |  | Mohamed Ayyash
9 | AP | 4 | Space | To be updated. | Process | Close |  | Mohamed Ayyash